## Project Summary
PROJECT SUMMARY AND DESCRIPTION
FOR: (FOR EACH PROJECT FROM 2025-27 CAPITAL REQUEST SCHEDULE: EXCLUDE R&R)
Institution: | Ivy Tech Community College |  |  |  |  | Budget Agency Project No.:
Campus: | Terre Haute |  |  |  |  | Institutional Priority:
Previously approved by General Assembly: |  |  |  | No |  | Previously recommended by CHE: |  |  | No
Part of the Institution's Long-term Capital Plan: |  |  |  | Yes
Project Summary Description:
In 2025, the Terre Haute campus was Ivy Tech’s top request for capital project funding presented to the Indiana General Assembly. Unfortunately, the General Assembly did not fund institutional capital projects. However, the College's capital needs still exist. As such, the Terre Haute campus will use college unrestrictred net assets and fundraising dollars to move forward with a portion of the essential renovations needed to support the School of Health Sciences. The proposed renovations are aligned with the original capital project that the College presented to the Commission and legislature. This renovation will occur in the newest part of the building, the Center for Information Technology (CIT), which the College added in 2002. The health sciences programs that will be relocated into the renovated space are surgical technology, medical laboratory technology, and radiologic technology, and are all currently located in the section of our campus built in 1967. The current academic space for these programs does not provide an optimal instructional environment and limits the ability to grow enrollment or upgrade equipment to the latest industry needs.
Summary of the impact on the educational attainment of students at the institution:
By converting the large classrooms into specialized instructional spaces, the project will enhance teaching and learning environments while also moving three health science programs into closer proximity to the previously renovated health science program spaces. This will also allow for room sharing and cross collaboration. Additionally, once the health sciences spaces are relocated into the newly renovated space in the CIT, we will be able to take many of the vacated classrooms, labs and offices offline, ensuring that we reduce the amount of student and staff space that are in the portions of our building that has extensive infrastructure issues and lacks some safety features like a sprinkler system. This renovation aligns with past strategic renovations, with the goal of establishing a healthcare wing in the CIT building where all health sciences and nursing programs will eventually be housed. This strategic renovation plan will foster interdisciplinary work, mirror the industry environment, and prepare our healthcare students for a seamless transition into the workforce.
Project Size: | 12554 | GSF | 9533 | ASF | 0.76 | ASF/GSF
Net change in overall campus space: |  |  | 0 | GSF | 0 | ASF
Total cost of the project (1): |  |  | 3000000.3 |  | Cost per ASF/GSF: |  | 238.9677 | GSF
[7 empty] | 314.6963 | ASF
Funding Source(s) for project (2): |  |  | Fundraising - $800,000 | - List amount and note the fund source/bonding authority here
|  |  | R & R - $1 million | - List amount and note the fund source/bonding authority here
|  |  | Unrestricted Net Assets - $1.2 million | - List amount and note the fund source/bonding authority here
- List amount and note the fund source/bonding authority here
Estimated annual debt payment (4):
Are all funds for the project secured: |  |  | No
Estimated annual change in cost of building operations based on the project: | [5 empty] | 0
Estimated annual repair and rehabilitation investment (3): |  |  |  |  | 0
(1) Projects should include all costs associated with the project (structure, A&E, infrastructure, consulting, FF&E, etc.)
(2) Be consistent in the naming of funds to be used for projects. If bonding, note Bonding Authority Year (1965, 1929, 1927, etc.)
(3) Estimate the amount of funding the institution would need to set aside annually to address R&R needs for the project. CHE suggests 1.5% of total construction cost
(4) If issuing debt, determine annual payment based on 20 years at 5.75% interest rate
- If project is a lease-purchase or lease, adjust accordingly. Note the total cost of the lease in the project cost, and annual payments in project description

## Detailed Description
PROJECT DETAILED DESCRIPTION - ADDITIONAL INFORMATION
FOR: (FOR EACH PROJECT FROM 2025-27 CAPITAL REQUEST SCHEDULE: EXCLUDE R&R)
Institution: | Ivy Tech Community College | Budget Agency Project No.:
Campus: | Terre Haute | Institutional Priority:
Description of Project
The proposed project is is a small component of the previously requested extensive $64 million project. Without funding for the full campus renovation, the College is moving forward with small portion of the project that will allow the College to relocate three health sciences programs from areas of the building that continue to deteriote. The medical lab technology, surgical technology and medical imaging programs will be relocated to a newer portion of the building that is conducive to renovation. The original portion of the building where the programs are currently house was built in 1967 and has extensive infrastructure issues that would be near impossible to resolve with renovations. There is no sprinkler system in the original portion of the building, creating a safety issue that cannot be resolved with renovations. Plumbing issues are a recurring eyesore and hazard, with two restrooms that continue to have major failures and difficult repairs due to the plumbing running under a concrete slab foundation. The portion of the building built in mid 2002 will bet the new location for the programs. General classrooms will undergo extensive renovations to create state of the art lab spaces with the eventual goal of creating a healthcare wing, which would house the School of Health Sciences and the School of Nursing. However, this project is just a step in that direction with the full renovation requiring an extensive capital project in the future. The relocation and renovation for these three programs will create a more robust learning laboratory environment and interdisciplinary interaction and allows for future program growth. The School of Health Sciences has limited ability to expand program enrollment due to the confines of the current space.
Need and Purpose of the Program
Co-locating most of the School of Health Sciences programs will enable students to work in an integrated healthcare setting and experience cross-program collaboration, shared resources, and shared lab simulations. The local employers we serve count on Ivy Tech to produce highly skilled graduates to assist with meeting their workforce needs. They provide fundraising dollars, serve on advisory boards, and share the value our graduates provide to their companies. Our graduates stand out based on their technical skills, and that begins with practical labs that simulate employment settings. The health sciences programs at the Terre Haute campus continue to be listed as those projected to continue to be required in the future. These highly visible and high demand programs need to be in classroom and lab spaces that reflect the environments they will encounter when they enter the workforce. Moving from converted closets and other small spaces to state of the art laboratories will ensure they are prepared for the workforce. In addition, the new lab spaces will aid in recruitment as the potential students experience the working environment they will see in the career fields for the three program spaces being renovated. - Medical Imaging – this is a select admit program so an expansion would include an entire new cohort of 20. This past Spring, based on local demand, we added an additional cohort. The space constraints in the current space made this a challenge. However, the new space would allow this to be managed much more effectively. Based on demand, the additional cohort could be added. With the merger and expansion of Union Health, we continue to monitor demand. Because not all campuses have this program, we also monitor the service areas around us to ensure our output matches the need. Surgical Technology – this is also a select admit program with a cohort capacity of 16. Depending on the cohort, this program is often not at capacity. We feel confident the new space will serve as a recruitment tool that will lead to meeting capacity. In addition, with the merger and expansion of Union Health, we continue to monitor demand. Because not all campuses have this program, we also monitor the service areas around us to ensure our output matches the need. Medical Lab Technology - this is also a select admit program with the cohort capacity of 20. Depending on the cohort, this program is often not at capacity. We feel confident the new space will serve as a recruitment tool that will lead to meeting capacity. In addition, with the merger and expansion of Union Health, we continue to monitor demand. Because not all campuses have this program, we also monitor the service areas around us to ensure our output matches the need.
Space Utilization
Once the health sciences spaces are relocated into the newly renovated space in the CIT, we will be able to take many of the vacated classrooms, labs and offices offline, ensuring that we reduce the amount of student and staff space that are in the portions of our building that has extensive infrastructure issues, including lacking some safety features like a sprinkler system.
Comparable Projects
The Ivy Tech - Terre Haute campus does not have comparable projects in the recent history that are comparable in size and scope. ITCC has relied on our architectural partners and their estimating partners to provide cost esitmates for this project.
Background Materials
Pictures of existing spaces and a design book for the renovation and build project are included.

## Campus Space Details
CAPITAL PROJECT REQUEST FORM
INDIANA PUBLIC POSTSECONDARY EDUCATION
INSTITUTION CAMPUS SPACE DETAILS FOR Terre Haute
(INSERT PROJECT TITLE AND SBA No.) | Current Space in Use | Space Under Construction (1) | Space Planned and Funded (1) | Subtotal Current and Future Space | Space to be Terminated (1) |  | New Space in Capital Request (2) | Net Future Space
A. OVERALL SPACE IN ASF
Classroom (110 & 115) | 3735 | 0 | 0 | 3735 | 2323 |  | 2323 | 3735
Class Lab (210,215,220,225,230,235) | 4180 | 0 | 0 | 4180 | 5269 |  | 5269 | 4180
Non-class Lab (250 & 255) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Office Facilities (300) | 1618 | 0 | 0 | 1618 | 1978 |  | 1978 | 1618
Study Facilities (400) | 0 | 0 |  | 0 | 0 |  | 0 | 0
Special Use Facilities (500) | 0 | 0 |  | 0 | 0 |  | 0 | 0
General Use Facilities (600) | 0 | 0 |  | 0 | 0 |  | 0 | 0
Support Facilities (700) | 0 | 0 |  | 0 | 0 |  | 0 | 0
Health Care Facilities (800) | 0 | 0 |  | 0 | 0 |  | 0 | 0
Resident Facilities (900) | 0 | 0 |  | 0 | 0 |  | 0 | 0
Unclassified (000) | 0 | 0 |  | 0 | 0 |  | 0 | 0
B. OTHER FACILITIES
Walls/Chases | 0 | 0 |  | 0 | 0 |  | 0 | 0
Circulation | 3021 | 0 | 0 | 3021 | 2984 | 26075 | 2984 | 3021
TOTAL SPACE | 12554 | 0 | 0 | 12554 | 12554 |  | 12554 | 12554
Notes:
(1) Identify in a footnote the specific facilities that are included in the data in these columns. Do not include pending approval, non-submitted projects or non-funded projects
(2) Should include capital projects requested by the institution based on 2013-15 Capital Request Summary
- Space/Room codes based on Postsecondary Ed Facilities Inventory and Classification Manual (2006)

## Project Cost Details
CAPITAL PROJECT COST DETAILS
FOR: (FOR EACH PROJECT FROM 2013-15 CAPITAL REQUEST SCHEDULE: EXCLUDE R&R)
Institution: | Ivy Tech Community College |  |  | Budget Agency Project No.:
Campus: | Terre Haute |  |  | Institutional Priority:
ANTICIPATED CONSTRUCTION SCHEDULE
|  | Month | Year
| Bid Date | September | 2026
| Start Construction | January | 2027
| Occupancy (End Date) | December | 2027
ESTIMATED CONSTRUCTION COST FOR PROJECT
|  |  | Cost Basis (Nov 2025) | Estimated Escalation Factors (10%) | Project Cost
Planning Costs
| a. Combined A/E Fees |  | 354000 | 35400 | 389400
| b. Architectural |  |  |  | 0
| c. Consulting |  |  |  | 0
Construction
| a. Structure |  | 1814100 | 181410 | 1995510
| b. Mechanical (HVAC, plumbing, etc.) |  | 311420 | 31142 | 342562
| c. Electrical |  | 247753 | 24775.3 | 272528.3
| Movable Equipment |  | 0 | 0 | 0
| Fixed Equipment |  | 0 | 0 | 0
| Site Development/Land Acquisition |  | 0 | 0 | 0
Other (Please list)
| Demolition of Existing Building |  | 0 | 0 | 0
| Reimbursables |  | 0 | 0 | 0
Permitting/Plan Review Fees
Owner Expenses
| TOTAL ESTIMATED PROJECT COST |  | 2727273 | 272727.3 | 3000000.3
(1) Cost Basis is based on current cost prevailing as of: November 2025
(2) Explain in the Description of Project Section of the "Cap Proj Details" schedule the reasoning for estimated escalation factors

## Operating Cost Details
CAPITAL PROJECT OPERATING COST DETAILS
FOR: (FOR EACH PROJECT FROM 2013-15 CAPITAL REQUEST SCHEDULE: EXCLUDE R&R)
Institution: | Ivy Tech Community College |  |  | Budget Agency Project No.:
Campus: | Terre Haute |  |  | Institutional Priority:
[6 empty] | GSF OF AREA AFFECTED BY PROJECT | 308859
ANNUAL OPERATING COST/SAVINGS (1)
|  |  | Cost per GSF | Total Operating Cost | Personal Services | Supplies and Expenses
|  | 1. Operations | 0 | 0 | 0 | 0
|  | 2. Maintenance | 0 | 0 | 0 | 0
|  | 3. Fuel | 0 | 0 | 0 | 0
|  | 4. Utilities | 0 | 0 | 0 | 0
|  | 5. Other |  | 0
|  | TOTAL ESTIMATED OPERATIONAL COST/SAVINGS | 0 | 0 | 0 | 0
Description of any unusual factors affecting operating and maintenance costs/savings.
Demolition of the older buildings with lower standards of building envelope due to date of construction as well as a decrease in overall gross square footage will allow the college to realize costs savings in future utility expenses.
(1) Based on figures from "Individual Cap Proj Desc" schedule

## Space-Room Codes
ROOM USE CATEGORIES
(100) Classroom Facilities
110 Classroom
115 Classroom Service
(200) Laboratory Facilities
210 Class Laboratory
215 Class Laboratory Service
220 Open Laboratory
225 Open Laboratory Service
250 Research/Non-class Laboratory
255 Research/Non-class Laboratory Service
Note: 220 combines previous codes 220 and 230, 225 combines previous codes 225 and 235
(300) Office Facilities
310 Office
315 Office Service
350 Conference Room
355 Conference Room Service
(400) Study Facilities
410 Study Room
420 Stack
430 Open-Stack Study Room
440 Processing Room
455 Study Service
(500) Special Use Facilities
510 Armory
515 Armory Service
520 Athletic or Physical Education
523 Athletic Facilities Spectator Seating
525 Athletic or Physical Ed Service
530 Media Production
535 Media Production Service
540 Clinic
545 Clinic Service
550 Demonstration
555 Demonstration Service
560 Field Building
570 Animal Facilities
575 Animal Facilities Service
580 Greenhouse
585 Greenhouse Service
590 Other (All Purpose)
(600) General Use Facilities
610 Assembly
615 Assembly Service
620 Exhibition
625 Exhibition Service
630 Food Facility
635 Food Facility Service
640 Day Care
645 Day Care Service
650 Lounge
655 Lounge Service
660 Merchandising
665 Merchandising Service
670 Recreation
675 Recreation Service
680 Meeting Room
685 Meeting Room Service
Note: 640 Day Care and 645 Day Care Service added. 690 Locker Room deleted; reassign to 115,215,225,315
690 Locker Room deleted; reassign to 115,215,225,315 or other room service code.
(700) Support Facilities
710 Central Computer or Telecommunications
715 Central Computer or Telecommunications Service
720 Shop
725 Shop Service
730 Central Storage
735 Central Storage Service
740 Vehicle Storage
745 Vehicle Storage Service
750 Central Service
755 Central Service Support
760 Hazardous Materials Storage
770 Hazardous Waste Storage
775 Hazardous Waste Service
780 Unit Storage
(800) Health Care Facilities
810 Patient Bedroom
815 Patient Bedroom Service
820 Patient Bath
830 Nurse Station
835 Nurse Station Service
840 Surgery
845 Surgery Service
850 Treatment/Examination Clinic
855 Treatment/Examination Clinic Service
860 Diagnostic Service Laboratory
865 Diagnostic Service Lab Support
870 Central Supplies
880 Public Waiting
890 Staff On-Call Facility
895 Staff On-Call Facility Service
Note: Previous 895, Health Care Service deleted. Apply appropriate service code to primary room code.
(900) Residential Facilities
910 Sleep/Study w/o Toilet or Bath
919 Toilet or Bath
920 Sleep/Study w/Toilet or Bath
935 Sleep/Study Service
950 Apartment
955 Apartment Service
970 House
(000) Unclassified Facilities
050 Inactive Area
060 Alteration or Conversion Area
070 Unfinished Area
Note: Each bracketed room use category may be aggregated for academic/administrative space as well as
supplementary space.
From: Postsecondary Education Facilities Inventory and Classification Manual
(NCES,2006)