## Project Summary
PROJECT SUMMARY AND DESCRIPTION
FOR: STEAM PLANT RENOVATION
Institution: | Vincennes University |  |  |  |  | Budget Agency Project No.: |  |  | E-1-21-2-01
Campus: | Vincennes |  |  |  |  | Institutional Priority:
Previously approved by General Assembly: | [5 empty] | Previously recommended by CHE:
Part of the Institution's Long-term Capital Plan: |  |  |  | Yes
Project Summary Description:
This project will replace two of the three steam boilers in Vincennes University's central steam plant. The two boilers have reached the end of their serviceable lifecycle. Boiler One is 32 years old and Boiler Two is 42 years old - both have required several major patches and repairs to keep them functional. Both boilers will be replaced with new, higher capacity boilers that are expected to be 10 to 15% more efficient than their predecessors. The boiler replacements will require extensive re-piping and replacements of chemical treatment systems. Emergency connections will also be added that will allow for operation in the case of a catastrophic event that may otherwise render the steam plant inoperable.
Summary of the impact on the educational attainment of students at the institution:
This special renovation project addresses critical maintenance for utility needs across the institution. The Steam Plant Renovation has been identified as a core project that will not only provide basic heating and hot water for classrooms but will utilize modern systems that operate in a much more efficient and cost-effective manner. The existing boilers in the steam plant have simply reached the end of their lifecycle and need replaced to maintain comfort in academic buildings without interruption due to emergency repairs. Vincennes University has placed special attention on projects that replace outdated mechanical systems with modern, code compliant, efficient, maintenance friendly, and cost-effective systems in order to provide a quality educational environment.
Project Size: | NA | GSF | NA | ASF | NA | ASF/GSF
Net change in overall campus space: |  |  | NA | GSF | NA | ASF
Total cost of the project (1): |  |  | 3500000 |  | Cost per ASF/GSF: |  | NA | GSF
[7 empty] | NA | ASF
Funding Source(s) for project (2): |  |  | 3500000 | - University Reserves
Estimated annual debt payment (4):
Are all funds for the project secured: |  |  | Yes
Estimated annual change in cost of building operations based on the project: | [5 empty] | -68000
Estimated annual repair and rehabilitation investment (3):
(1) Projects should include all costs associated with the project (structure, A&E, infrastructure, consulting, FF&E, etc.)
(2) Be consistent in the naming of funds to be used for projects. If bonding, note Bonding Authority Year (1965, 1929, 1927, etc.)
(3) Estimate the amount of funding the institution would need to set aside annually to address R&R needs for the project. CHE suggests 1.5% of total construction cost
(4) If issuing debt, determine annual payment based on 20 years at 5.75% interest rate
- If project is a lease-purchase or lease, adjust accordingly. Note the total cost of the lease in the project cost, and annual payments in project description

## Detailed Description
PROJECT DETAILED DESCRIPTION - ADDITIONAL INFORMATION
FOR: STEAM PLANT RENOVATION
Institution: | Vincennes University | Budget Agency Project No.: | E-1-21-2-01
Campus: | Vincennes | Institutional Priority:
Description of Project
Vincennes University is serviced by a central steam plant that provides heat and hot water to many of the facilities on the Vincennes campus. The Steam Plant Renovations are a needed continuation of the work that was completed in Phase I and Phase II of the steam line replacement project that replaced 10,700 lineal feet of steam line. The work that was completed reduced water usage by 55%, resulting in a savings of $90,000 annually. This project will now replace two of the three steam boilers in the central steam plant. The two boilers have reached the end of their serviceable lifecycle. Boiler One is 32 years old and Boiler Two is 42 years old - both have required several major patches and repairs to keep them functional. Both boilers will be replaced with new, higher capacity boilers that are expected to be 10 to 15% more efficient than their predecessors. The boiler replacements will require extensive re-piping and replacement of chemical treatment systems. Emergency connections will also be added that will allow for operation in the case of a catastrophic event that may otherwise render the steam plant inoperable.
Need and Purpose of the Program
This special renovation project addresses critical maintenance for utility needs across the institution. The Steam Plant Renovation has been identified as a core project that will not only provide basic heating and hot water for classrooms, but will utilize modern systems that operate in a much more efficient and cost-effective manner. The existing boilers in the steam plant, have simply reached the end of their lifecycle and need replaced to maintain comfort in academic buildings without interruption due to emergency repairs. Vincennes University has placed special attention on projects that replace outdated mechanical systems with modern, code compliant, efficient, maintenance friendly, and cost-effective systems in order to provide a quality educational environment.
Space Utilization
This project will not add any additional square footage to the campus.
Comparable Projects
Vincennes University has completed HVAC, electrical and communication upgrades to many of its facilities in recent years including the $10,300,000 mechanical upgrades to Shircliff Humanities Center and the Phillip M. Summers Center in 2019. The Steam Plant Renovations Project is a continuation of the work that was completed in Phase I and Phase II that replaced 10,700 lineal feet of steam line.
Background Materials

## Campus Space Details
CAPITAL PROJECT REQUEST FORM
INDIANA PUBLIC POSTSECONDARY EDUCATION
INSTITUTION CAMPUS SPACE DETAILS FOR Vincennes University Steam Plant Renovation
Steam Plant Renovation (E-1-21-2-01) | Current Space in Use | Space Under Construction (1) | Space Planned and Funded (1) | Subtotal Current and Future Space | Space to be Terminated (1) | New Space in Capital Request (2) | Net Future Space
A. OVERALL SPACE IN ASF
Classroom (110 & 115) |  |  |  | 0 |  |  | 0
Class Lab (210,215,220,225,230,235) |  |  |  | 0 |  |  | 0
Non-class Lab (250 & 255) |  |  |  | 0 |  |  | 0
Office Facilities (300) |  |  |  | 0 |  |  | 0
Study Facilities (400) |  |  |  | 0 |  |  | 0
Special Use Facilities (500) |  |  |  | 0 |  |  | 0
General Use Facilities (600) |  |  |  | 0 |  |  | 0
Support Facilities (700) |  |  |  | 0 |  |  | 0
Health Care Facilities (800) |  |  |  | 0 |  |  | 0
Resident Facilities (900) |  |  |  | 0 |  |  | 0
Unclassified (000) |  |  |  | 0 |  |  | 0
B. OTHER FACILITIES
(Please list major categories) |  |  |  | 0 |  |  | 0
TOTAL SPACE | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
(1) Identify in a footnote the specific facilities that are included in the data in these columns. Do not include pending approval, non-submitted projects or non-funded projects
(2) Should include capital projects requested by the institution based on 2013-15 Capital Request Summary
- Space/Room codes based on Postsecondary Ed Facilities Inventory and Classification Manual (2006)

## Project Cost Details
CAPITAL PROJECT COST DETAILS
FOR: STEAM PLANT RENOVATION
Institution: | Vincennes University |  |  | Budget Agency Project No.: |  | E-1-21-2-01
Campus: | Vincennes |  |  | Institutional Priority:
ANTICIPATED CONSTRUCTION SCHEDULE
|  | Month | Year
| Bid Date | March | 2026
| Start Construction | May | 2026
| Occupancy (End Date) | August | 2026
ESTIMATED CONSTRUCTION COST FOR PROJECT
|  |  | Cost Basis (1) | Estimated Escalation Factors (2) | Project Cost
Planning Costs
| a. Engineering |  | 175000 |  | 175000
| b. Architectural |  |  |  | 0
| c. Consulting |  |  |  | 0
Construction
| a. Structure |  | 200000 |  | 200000
| b. Mechanical (HVAC, plumbing, etc.) |  | 2900000 |  | 2900000
| c. Electrical |  | 225000 |  | 225000
| Movable Equipment |  |  |  | 0
| Fixed Equipment |  |  |  | 0
| Site Development/Land Acquisition |  |  |  | 0
| Other (Please list) |  |  |  | 0
| TOTAL ESTIMATED PROJECT COST |  | 3500000 | 0 | 3500000
(1) Cost Basis is based on current cost prevailing as of: July 2025
(2) Explain in the Description of Project Section of the "Cap Proj Details" schedule the reasoning for estimated escalation factors

## Operating Cost Details
CAPITAL PROJECT OPERATING COST DETAILS
FOR: STEAM PLANT RENOVATION
Institution: | Vincennes University |  |  | Budget Agency Project No.: |  |  | E-1-21-2-01
Campus: | Vincennes |  |  | Institutional Priority:
[6 empty] | GSF OF AREA AFFECTED BY PROJECT | N/A
ANNUAL OPERATING COST/SAVINGS (1)
|  |  | Cost per GSF | Total Operating Cost | Personal Services | Supplies and Expenses
|  | 1. Operations | NA | 0
|  | 2. Maintenance | NA | 0
|  | 3. Fuel | NA | 0
|  | 4. Utilities | NA | -68000
|  | 5. Other | NA | 0
|  | TOTAL ESTIMATED OPERATIONAL COST/SAVINGS | NA | -68000 | 0 | 0
Description of any unusual factors affecting operating and maintenance costs/savings.
The upgrades to Vincennes University's steam plant facility will result in an estimated cost savings of $68,000 annually. This estimate is based on a 10% improvement in boiler efficiency.
(1) Based on figures from "Individual Cap Proj Desc" schedule

## Space-Room Codes
ROOM USE CATEGORIES
(100) Classroom Facilities
110 Classroom
115 Classroom Service
(200) Laboratory Facilities
210 Class Laboratory
215 Class Laboratory Service
220 Open Laboratory
225 Open Laboratory Service
250 Research/Non-class Laboratory
255 Research/Non-class Laboratory Service
Note: 220 combines previous codes 220 and 230, 225 combines previous codes 225 and 235
(300) Office Facilities
310 Office
315 Office Service
350 Conference Room
355 Conference Room Service
(400) Study Facilities
410 Study Room
420 Stack
430 Open-Stack Study Room
440 Processing Room
455 Study Service
(500) Special Use Facilities
510 Armory
515 Armory Service
520 Athletic or Physical Education
523 Athletic Facilities Spectator Seating
525 Athletic or Physical Ed Service
530 Media Production
535 Media Production Service
540 Clinic
545 Clinic Service
550 Demonstration
555 Demonstration Service
560 Field Building
570 Animal Facilities
575 Animal Facilities Service
580 Greenhouse
585 Greenhouse Service
590 Other (All Purpose)
(600) General Use Facilities
610 Assembly
615 Assembly Service
620 Exhibition
625 Exhibition Service
630 Food Facility
635 Food Facility Service
640 Day Care
645 Day Care Service
650 Lounge
655 Lounge Service
660 Merchandising
665 Merchandising Service
670 Recreation
675 Recreation Service
680 Meeting Room
685 Meeting Room Service
Note: 640 Day Care and 645 Day Care Service added. 690 Locker Room deleted; reassign to 115,215,225,315
690 Locker Room deleted; reassign to 115,215,225,315 or other room service code.
(700) Support Facilities
710 Central Computer or Telecommunications
715 Central Computer or Telecommunications Service
720 Shop
725 Shop Service
730 Central Storage
735 Central Storage Service
740 Vehicle Storage
745 Vehicle Storage Service
750 Central Service
755 Central Service Support
760 Hazardous Materials Storage
770 Hazardous Waste Storage
775 Hazardous Waste Service
780 Unit Storage
(800) Health Care Facilities
810 Patient Bedroom
815 Patient Bedroom Service
820 Patient Bath
830 Nurse Station
835 Nurse Station Service
840 Surgery
845 Surgery Service
850 Treatment/Examination Clinic
855 Treatment/Examination Clinic Service
860 Diagnostic Service Laboratory
865 Diagnostic Service Lab Support
870 Central Supplies
880 Public Waiting
890 Staff On-Call Facility
895 Staff On-Call Facility Service
Note: Previous 895, Health Care Service deleted. Apply appropriate service code to primary room code.
(900) Residential Facilities
910 Sleep/Study w/o Toilet or Bath
919 Toilet or Bath
920 Sleep/Study w/Toilet or Bath
935 Sleep/Study Service
950 Apartment
955 Apartment Service
970 House
(000) Unclassified Facilities
050 Inactive Area
060 Alteration or Conversion Area
070 Unfinished Area
Note: Each bracketed room use category may be aggregated for academic/administrative space as well as
supplementary space.
From: Postsecondary Education Facilities Inventory and Classification Manual
(NCES,2006)