# Attachment K - AFIS Statement of Work

- Contents

I.	EXECUTIVE SUMMARY	3

a.	OVERVIEW	3

b.	PURPOSE AND BENEFITS	3

II.	BACKGROUND AND CURRENT STATE	3

a.	CURRENT DESCRIPTION OVERVIEW	3

b.	CURRENT BUSINESS PROCESS FLOWS	4

III.	SCOPE OF WORK	5

a.	OBJECTIVES OF THE ENGAGEMENT	5

b.	TECHNICAL REQUIREMENTS	6

c.	DESIRED FUTURE STATE	7

d.	PROJECT EXCLUSIONS	9

e.	DELIVERABLES AND DEADLINES	9

f.	PAYMENT MILESTONES	10

IV.	PROJECT MANAGEMENT	11

a.	PROJECT MANAGEMENT PLAN	11

b.	KEY PERSONS	12

c.	OTHER PROJECT STAFF	17

d.	DOCUMENT MANAGEMENT	18

e.	STATUS UPDATES AND REPORTING	18

f.	ORGANIZATIONAL CHANGE MANAGEMENT (OCM)	19

V.	INDEPENDENT VERIFICATION AND VALIDATION	19

VI.	COMPLIANCE REQUIREMENTS	19

a.	SECURITY POLICIES AND STANDARDS	19

b.	ARTIFICIAL INTELLIGENCE STANDARDS	20

c.	ACCESSIBILITY	20

d.	DATA EXCHANGE	20

e.	AUTHENTICATION	20

VII.	KEY PERFORMANCE INDICATORS (KPIs)	20

VIII.	MAINTENANCE AND OPERATIONS (M&O)	21

IX.	END OF CONTRACT TRANSITION AND TURNOVER	22

X.	SERVICE LEVELS AND PERFORMANCE REMEDIES	24

a.	SYSTEM AVAILABILITY	24

b.	DISASTER RECOVERY	24

c.	INCIDENT RESPONSE AND RESOLUTION	25

d.	DEFECT RESOLUTION (POST GO-LIVE)	25

e.	REPORTING REQUIREMENTS	26

f.	LIQUIDATED DAMAGES AND PERFORMANCE ENFORCEMENT	26

# EXECUTIVE SUMMARY

## OVERVIEW

Indiana’s Automated Fingerprint Identification System (AFIS) is the State’s critical platform for processing all criminal and applicant fingerprint submissions from 92 county jails, public livescan sites, and courts, while supporting latent print examination and exchanges with the Federal Bureau of Investigation’s (FBI) Next Generation Identification (NGI) system. The State is undertaking a modernization initiative to transition AFIS from aging, on-premises infrastructure to a secure, scalable solution that maintains all existing workflows and integrations, including the Computerized Criminal History (CCH) system, Multi-Biometric Identification System (MBIS), NGI system, and Indiana State Police (ISP) systems, without disrupting statewide operations.

## PURPOSE AND BENEFITS

The purpose of this engagement is to implement a modern AFIS platform that improves performance, reliability, interoperability, and security while supporting growing biometric data volumes and increasing operational demands. The modernized solution will reduce manual processing, strengthen lights‑out capabilities, enhance exception handling and monitoring, improve data integrity and reporting, and ensure continued compliance with State and Federal security requirements. This initiative is expected to be completed within 18 months, following a structured Hybrid Agile approach with defined deliverables, acceptance criteria, and governance controls to ensure transparency and successful statewide adoption.

# BACKGROUND AND CURRENT STATE

## CURRENT DESCRIPTION OVERVIEW

The current AFIS environment processes fingerprint-based submissions originating from electronic fingerprint capture sites throughout the State of Indiana and all 92 county jails. AFIS functions as the front door to Indiana’s criminal history process and remains one of the most critical systems within ISP operations. Submissions initiate an automated workflow that culminates in review and processing by fingerprint analysis personnel.

AFIS serves as a central point of integration for multiple criminal justice systems. It receives, validates, and routes National Institute of Standards and Technology (NIST)-formatted transactions; interacts with the State’s CCH system; supports latent print examination and comparison; and exchanges biometric and related data with the FBI’s NGI system. If a latent print does not result in an identification it is registered within AFIS and is automatically searched against all new criminal fingerprint submissions received by AFIS. AFIS also supports interfaces with local MBIS installations and various law enforcement, judicial, and applicant processing entities statewide.

AFIS data includes Criminal Justice Information (CJI) containing Personally Identifiable Information (PII). The current repository contains over 15 million biometric items (fingerprints, palm prints, mugshots, and photographs) and occupies approximately 27 TB of storage, with planned growth to 35 TB over the next five (5) years. In the 2025 reporting year AFIS processed 381,163 total fingerprint submissions across criminal and applicant workflows (Criminal Fingerprints: 185,345 / Applicant Fingerprints: 195,818).

Current AFIS Components and Interfaces

The current AFIS environment includes the following primary capabilities, components, and system interfaces required to support statewide biometric processing operations:

- Fingerprinting

  - Reporting and Analytics

  - User Access / User Interfaces

  - Existing interfaces

    - CCH

    - Card Scanner

    - Universal Latent Workstation (ULW) to FBI

    - NEC MBIS:

      - Indianapolis Metro Police Department (PD)

      - South Bend PD

      - Fort Wayne PD

    - FBI NGI system

    - Livescans

    - County Jails

    - Department of Corrections

    - Police Departments

    - Courts

    - Applicant Livescans

    - Gaming Riverboats

    - ISP Records Management System (RMS)

These capabilities support AFIS's ongoing role as a statewide biometric processing hub, maintaining essential connections between State, local, and Federal criminal justice partners. The current AFIS environment operates on 26 physical servers that support the full set of statewide processing activities. Additional detail is provided in Attachment N – AFIS Equipment Listing.

## CURRENT BUSINESS PROCESS FLOWS

The existing business process flows for AFIS are documented as follows:

- Workflow Narrative

  - Criminal NIST created and sent from livescan to:

    - Local AFIS (3 counties)-prints are completed at the local AFIS and then sent to the State AFIS. The processes are completed at the state level as if it came directly from a livescan State AFIS system.

  - Data in NIST validated by CCH system:

    - Rejected - Response sent back to livescan & CCH system, transaction complete (no further processing is done)

    - Accepted - Fingerprints are then processed either through lights out or human intervention through AFIS

  - Prints of sufficient quality completed in Ten print process and a search of the latent data base is executed.

    - If prior criminal history, arrest information is added to State number in both AFIS archive (data, mugshots & prints) and CCH system (data only), prints sent to NGI system for processing

    - If there is no prior history, a State number is created by AFIS with arrest data being added in both AFIS archive (data, mugshots & prints) and CCH system (data only), prints sent to NGI system

  - Prints of insufficient quality-Rejected & response sent back to livescan & CCH system, transaction complete (no further processing is done)

AFIS also supports the following additional workflow categories:

- NIST Tenprint Inquiry (TI) Workflow

  - Criminal arrest event workflow:

    - CAR: Search local, search FBI, retain both local & FBI

  - Applicant background check workflows:

    - Non-Federal Applicant User Fee (NFUF): Search local, Search FBI, retain local only

    - Miscellaneous Applicant Civil (MAP): Search local, Search FBI, retain local only

    - State Miscellaneous Applicant Civil (SMAP): Search local and retain local

- Non-NIST TI Workflow

  - AFIS Submissions- manual AFIS only identification and registry

  - TI Submissions-manual

- Latent Workflows

  - Latent Combo

  - Latent Palm Combo

  - ULW Inbound

  - ULW Outbound

  - LI-latent manual inquiry

- Mobile 2-Finger Search Workflow (also known as Fast ID)

Review Attachment O - AFIS Workflow to view the current workflow diagram. Within the workflow diagram, please note the following when reviewing:

- Criminal History Record Information System (CHRIS)

- Next Generation Identification (NGI)

- Transaction Control Number (TCN) / Type of Transaction (TOT):

# SCOPE OF WORK

## OBJECTIVES OF THE ENGAGEMENT

The State will modernize AFIS to ensure reliable statewide operations and long-term sustainability. The objectives are listed below. See Attachment P –Requirements Matrix for additional general and functional requirements.

- Migrate AFIS from aging on premises components to a secure and scalable cloud environment.

- Maintain all existing AFIS workflows during migration. This includes criminal processing, applicant processing, TI processing, latent examination, and ULW exchanges. No interruption to statewide operations will be permitted.

- Improve system performance and reliability. Provide strong monitoring. Provide timely identification of exceptions. Provide consistent resolution of issues.

- Strengthen interoperability with State and Federal criminal justice systems. Interfaces must remain fully supported. This includes CCH system, local MBISs, NGI system, RMS, and other agency systems connected to AFIS.

- Enhance security. Protect biometric and personal information.

- Meet Criminal Justice Information Services (CJIS) and CJI requirements.

- Meet the Indiana Office of Technology (IOT) requirements and supports the Risk and Authorization Management Program (RAMP) policy.

- Reduce manual processing. Enable lights out processing where appropriate. Minimize rejections through improved quality and validation.

- Provide a maintainable and Vendor supported solution. Favor configuration over custom code. Support future enhancements through configuration when possible.

- Define clear governance. Set deliverables. Set acceptance criteria. Set schedule expectations. Set reporting requirements. Enable transparent management of scope and lifecycle activities.

- Support scalability for data growth from the current size to the projected size within five (5) years.

- Enable a smooth transition of operations. Provide training and documentation. Ensure operational readiness. Support handoff to State personnel and future Vendors.

Administrative Module

The State’s preference is that the proposed system includes a comprehensive administrative module that allows authorized personnel to manage, monitor, and configure system functionality. The administrative module should be accessible through a secure, role‑based interface. It should support both centralized and distributed administration to align with the State’s operational and governance structure.

## TECHNICAL REQUIREMENTS

The State strongly prefers a cloud-based service offering. Cloud-based service offerings are required to be within a state-owned cloud tenant. However alternative solutions may be considered if they demonstrate significant value. This section provides details on infrastructure and support requirements, outlining the State’s minimum requirements. Review and completed Attachment M – Infrastructure Overview for more detailed information.

The State prefers a solution that meets requirements in the following priority order: out of the box functionality; configuration; or customization only as a last resort. Respondents shall complete Attachment P –Requirements Matrix to indicate whether each requested function is available Out-of-the-Box, can be met through Configuration, requires Customization, is Planned for future release, or is Not Addressed. For all customizations, Respondents must identify whether the enhancement will be incorporated into the core product going forward. For items marked “Not Possible,” Respondents must specify whether future roadmap support is planned.

The State expects the selected vendor to act as a partner to help identify potential business process changes that leverage out of the box or configuration options and reduce or eliminate the need for custom code. To help facilitate this, the selected vendor must document the out of the box and configuration options evaluated before proposing any customization and must demonstrate why configuration cannot satisfy the requirement.

Customizations should be considered only when one or more of these criteria apply: the requirement is necessary to meet a federal reporting requirement or regulation; the requirement is necessary to meet a state law, regulation, or rule; the requirement is necessary to satisfy state security requirements; the requirement is necessary to interface or integrate with state systems; or the requirement will produce a material improvement in service delivery, partner interactions, or utilization of state resources. Material improvements must be documented, justified, and presented to the Project Steering Committee for review.

All customizations require written approval from the Project Steering Committee before work begins. Each customization proposal must include a configuration first analysis, a functional specification, a technical design, an impact analysis addressing maintenance, upgrade compatibility, security, performance, accessibility, total cost of ownership, a test plan, a rollback plan, schedule impact, overall risk analysis, decision regarding adding to the core product functionality and why, and itemized pricing if applicable. Approved customizations must pass the same acceptance tests as core functionality, be upgrade compatible or provide a documented migration path, and meet State security standards. The vendor will deliver source code, developer and user documentation, and a perpetual royalty free license for any custom code. Additionally, the State expects the vendor to consider approved and implemented customizations for incorporation into the selected vendor core solution going forward so that they become out of the box functionality.

High Level Functional Requirements

- Provide native data migration, conversion and optimization to new algorithms, ensuring data integrity.

- Provide seamless communication with local agency MBISs in Indiana, including but limited to: Marion County SO/IMPD, Fort Wayne PD/Allen County and South Bend/St. Joseph County.

- Ability to migrate existing workflows to Cloud hosted system.

- Maintain in-state technicians capable of providing on-site service within SLA determined timeframes.

- FastID, fixed and mobile rapid identification for Public Safety agencies, compatible with existing systems workflows regional agencies in Indianapolis/Marion County, Fort Wayne/Allen County and South Bend/St. Joseph County.

- Support FastID capability for both fixed and mobile rapid identification use cases for public safety agencies across Indiana.

- Maintain all existing AFIS interfaces listed in the Current State section.

- Maintain all legacy interface and data sharing mechanisms for the duration of the contract.

- Maintain any new interfaces or data sharing mechanisms created during the engagement.

- Support all AFIS workflow types beyond NIST, including Non‑NIST, AFIS submissions, TI submissions, latent workflows, and ULW in/out.

- Support all State and Federal reporting requirements, including legacy reports.

- Support the continuation and maintenance of legacy reporting requirements for State and Federal partners.

- Support the creation and maintenance of new reporting requirements throughout the contract term.

- Support the continuation and maintenance of new interface and data sharing requirements.

- Support new and updated interface and data‑sharing requirements over time.

- Support Hybrid Agile SDLC delivery, including required artifacts and proven functionality delivered after each sprint for testing purposes.

- Provide Incident and Problem Management operations aligned to the State’s governance.

- Support statewide Data Warehouse / ODS / Data Mart management for reporting use cases.

- Support the State’s operational data store and data mart needs used for analytical reporting and summary level data access.

High Level Technical Requirements

- The initial database size is estimated to be around 27 TB.  The scope is to allow for expandability to approximately 35 TB within five (5) years.

- Support standardized data migration.

- Expectation to integrate with Access Indiana single sign‑on.

- Comply with State Information Security Framework (ISF) beyond RAMP requirements.

- Comply with Assistive Technology accessibility standards in the ISF, as required.

- Comply with State AI Policy and complete required AI Readiness Assessment.

- Require CJIS Security Addendum and annual CJIS awareness training for all personnel.

SDLC and Testing Requirements

- Use a hybrid Agile approach that includes regular and reoccurring demos of the solution delivered to team members that represent the various stakeholders that will be using the solution in some capacity.

- Provide a Master Test Plan.

- Define entry and exit criteria.

- Own unit testing, system testing, performance testing, security testing, integration testing, and support User Acceptance Testing (UAT).

- The State will work with the vendor in supporting the testing of data as part of the conversion and migration to confirm all in-scope data is converted/migrated and with highest quality to meet State expectations.

- Own defect management while producing defect logs and resolution tracking reports and dashboards.

- Provide post migration and post implementation validation.

- If the State decides to add external Testing Services Partner as part of this engagement, the Vendor will copy the Testing Services Partner team member(s) on all appropriate project related communications (emails, meeting invites, collaboration tools, etc.) and will grant access to all documents and deliverables throughout the term of the contract. Vendor will partner with the Testing Services Partner to ensure the solution is delivered to the Agency with the highest quality.

## DESIRED FUTURE STATE

The modernized AFIS will operate in a secure and scalable cloud environment. It will support the full scope of Indiana biometric processing needs. The platform will migrate all existing workflows without disruption. The modernized AFIS will maintain and strengthen interoperability with CCH system, local MBISs, NGI system, and other ISP systems connected to AFIS. The modernization will refine processes, enhance security, improve workflow efficiency, and strengthen interfaces with internal and external systems.

The State expects implementation to be completed within eighteen months. The Vendor will use a hybrid Agile approach with regular demonstrations and defined governance. The project team will include training and knowledge transfer to ensure readiness for operations.

AFIS future workflows that must be supported include criminal arrest events, TI processing, applicant background checks, non NIST TI processing, latent processing, ULW inbound and outbound, and manual inquiries. Mobile 2-finger search may be considered an optional workflow.

Future-State AFIS Workflows
The modernized AFIS must support the full set of workflows currently in use across Indiana criminal justice operations. These workflows form the basis for functional and technical requirements and will guide the Vendor’s design and implementation activities. Workflows to be supported include the items listed below.

Criminal and TI Workflows

- NIST TI Workflow

- Criminal Arrest Event Workflow that searches local and Federal repositories and retains both local and FBI records when required

Applicant Background Check Workflows

- Non-Federal Applicant User Fee processing

- Miscellaneous Applicant Civil processing

- State Miscellaneous Applicant Civil processing

Non NIST and Manual Print Processing

- Non-NIST TI Workflow

- AFIS manual identification submissions

- TI inquiry submissions

Latent Workflows

- Latent Combo processing

- Latent Palm Combo processing

- ULW inbound transactions

- ULW outbound transactions

- Latent manual inquiry processing

Workflow

- Mobile 2-finger rapid search workflow when requested by the State.

These workflow requirements form the basis for the functional and technical requirements used by the ISP CJIS/AFIS unit and the Vendor’s project team during design and implementation.

## PROJECT EXCLUSIONS

The following items are excluded from this engagement: Services outlined in Quantity Purchase Agreement (QPA) 71766 with IDEMIA (https://www.in.gov/idoa/proc/QPA/71766.pdf.

## DELIVERABLES AND DEADLINES

The Vendor shall provide, at a minimum, the following deliverables according a mutually agreed upon schedule. Each deliverable must include the required compliance evidence and will be subject to formal review and approval by the State. Deliverables should be submitted in both editable and PDF formats and stored in a state-owned repository.

Deliverables with Acceptance Criteria include, but are not limited to:

- Project Kickoff Package
Includes kickoff agenda, team organization chart, and communication plan.
Acceptance Criteria: Signed kickoff meeting minutes and list of State participants, and approved organization chart and communication plan.

- Requirements and Needs Assessment
Includes a detailed requirements document.
Acceptance Criteria: Formal sign-off of detailed requirements document by the State.

- Requirements Traceability Matrix (RTM)

Includes a comprehensive mapping of all functional, technical, and security requirements to design elements, test cases, and deployment activities.

Acceptance Criteria: RTM shows full coverage and traceability and is approved by the State.

- Project Plan and Schedule
Includes detailed and integrated tasks owned by the Vendor, the State, and any other vendor that is participating on the project, milestones, resource allocation, and critical path analysis.  
Acceptance Criteria: Approved baseline schedule and resource plan.

- Updated Project Schedule (Major Phases)

Includes updated schedules at each major phase reflecting approved changes, dependencies, and critical path revisions.

Acceptance Criteria: Updated schedule submitted in approved format and accepted by the State.

- Architecture & Design Package

Includes system architecture diagrams, interface specifications, data flow models, and detailed design documentation.

Acceptance Criteria: Design documents are internally consistent, traceable to requirements, peer‑reviewed, and approved by the State.

- Design or Prototype Documentation
Includes conceptual models, wireframes, or engineering drawings.
Acceptance Criteria: Demonstration of prototype and documented feedback log.

- Technical or Implementation Specifications
Includes configuration details, integration points, and data flows.
Acceptance Criteria: Peer review completed and State approval received.

- Data Conversion & Migration Package

Includes an overarching data migration plan, data mapping documents, conversion scripts, transformation rules, audit logs, RACI, and pre‑/post‑migration reconciliation reports.

Acceptance Criteria: Data migration plan approved by the State before any data conversion/migration begins. Reconciliation confirms completeness and accuracy of migrated data and associated documents; approved by the State prior to go‑live.

- Master Test Plan

Includes testing strategy, RACI, defect management, environments, entry/exit criteria, reference to test data availability and usage, and coverage of all test cycles including unit, system, performance, security, integration, and UAT.

Acceptance Criteria: Approved by the State before any testing activities begin

- Test Plan and Quality Assurance Results
Includes comprehensive test cases using the RTM, pass/fail results, and defect logs.
Acceptance Criteria: All critical, high, and medium defects resolved or approved waiver documented.

- Training and Knowledge Transfer Materials
Includes training plan, training guides, training delivery, recorded sessions, and competency sign-off forms.
Acceptance Criteria: Designated users confirm competency.

- Implementation & Deployment Plan

Includes go‑live sequence, detailed cutover steps, rollback plan, go/no‑go criteria, and deployment resourcing.

Acceptance Criteria: State approval received prior to implementation

- Deployment / Handover Package
Includes operational procedures, deployment checklist, and rollback plan.
Acceptance Criteria: Successful production cutover and verification completed.

- Hypercare

Includes heightened support to stabilize the solution post go-live for the period defined in the maintenance and operations section.

Acceptance Criteria: A stable solution in production with all critical and high defects corrected and approved in production.

- Final Report and Closeout Documentation
Includes as-built documentation and lessons learned.
Acceptance Criteria: Formal closeout sign-off by the State.

- Warranty and Maintenance Transition Documentation
Includes service level agreements, support contacts, and escalation procedures.
Acceptance Criteria: SLA executed and support process tested.

## PAYMENT MILESTONES

Payments under this engagement will be tied to milestone completion and formal acceptance of deliverables by the State. No payments will be issued for initial activities such as project kickoff. Instead, payment will occur after milestone three, covering all work completed up to that point. Subsequent payments will be made upon acceptance of each major deliverable as outlined in the Deliverables and Deadlines Section. Invoices must reference the accepted Milestone number and Deliverable Covered, the date of acceptance, and include the acceptance record and any required compliance evidence.

The State is prohibited from issuing advance payments for services, supplies, materials, or equipment unless expressly authorized under Indiana Code 4-13-2-20. Exceptions may apply for specific categories such as subscriptions, license fees, or insurance premiums, subject to prior approval by the State Budget Agency. For full details, refer to Indiana Code 4-13-2-20.

| Milestone | Deliverable Covered | Payment % | Trigger Summary |
| --- | --- | --- | --- |
| 1 | Project Kickoff Package | - | No payment issued |
| 2 | Requirements / Needs Assessment + Requirements Traceability Matrix (RTM) | - | No payment issued |
| 3 | Project Plan and Schedule + Updated Project Schedule (initial baseline) | 30% | Acceptance of baseline schedule and resource plan (covers Milestones 1–3) |
| 4 | Architecture & Design Package + Design / Prototype | 10% | Prototype demo and approved design documentation |
| 5 | Technical/Implementation Spec | 10% | Peer review completed and State approval received |
| 6 | Master Test Plan + Test Plan & QA Results | 10% | Master Test Plan approved and critical defects resolved |
| 7 | Data Conversion & Migration Package + Training & Knowledge Transfer | 10% | Data reconciliation results approved and competency sign-off completed |
| 8 | Formal UAT completion and Signoff | 10% | Signoff of formal UAT completion. |
| 9 | Implementation & Deployment Plan + Deployment / Handover Package | 10% | Successful cutover and deployment approval |
| 10 | Final Report and Closeout | 5% | Formal closeout sign-off |
| 11 | Warranty / Maintenance Transition | 5% (retention) | SLA executed and support tested |

# PROJECT MANAGEMENT

## PROJECT MANAGEMENT PLAN

The Vendor will deliver a Project Management Plan within 4 weeks of the contract start. The Project Management Plan will guide the planning and execution of all activities under this engagement and will be reviewed and approved by the State. The Vendor will maintain the Project Management Plan as a living document and update it when required. The State anticipates assigning an internal Project Manager with whom the Vendor will coordinate all project-related activities.

The Project Management Plan will include, at a minimum, the items listed below.

Project Schedule

- The Vendor will develop a schedule that identifies milestones, tasks, dependencies, and resource assignments. The schedule will include both Vendor activities and any State activities that are required for completion. The Vendor will update the schedule at least weekly and provide visibility into critical path items.

Project Organization and Staffing

- The Vendor will describe the project team structure and roles. This includes key personnel, supporting personnel, reporting relationships, and communication expectations. The plan will describe the Vendor’s staffing approach and the process for replacing team members when necessary.

Requirements and Traceability Approach

- The Vendor will describe the approach for documenting requirements and maintaining traceability through the Requirements Traceability Matrix. The Matrix will track requirements through design, testing, and implementation. The Vendor will maintain the Matrix in the State’s Application Lifecycle Management tools.

Risk and Issue Management

- The Project Management Plan will describe how risks and issues are identified, documented, tracked, and escalated. A risk log and an issue log will be maintained throughout the engagement and updated as part of weekly status reporting.

Communication Plan

- The Vendor will describe how project information will be communicated. The plan will identify communication methods, meeting structure, reporting frequency, and stakeholder communication expectations. This includes weekly status meetings, monthly reviews, and quarterly business reviews.

Quality Management

- The Vendor will describe the quality standards and review processes used to ensure that project deliverables meet State expectations. The plan will describe how deliverables will be reviewed, approved, and updated when required.

Change Control Process

- The Vendor will describe the process for evaluating and approving changes. The process will follow State standards and will require a Change Impact Analysis before changes are approved. Work may not begin until the State provides written approval.

SDLC Overview

- The Vendor will briefly describe how hybrid Agile methods will be applied to design, development, testing, and deployment. More detailed expectations for SDLC and testing appear in project management and testing sections that follow.

Use of State Tools and Repositories

- The Vendor will use State approved tools for documentation, file storage, and artifact management. The State will provide repositories such as Teams, SharePoint, and Application Lifecycle Management tools. The Vendor will follow State naming and version standards.

## KEY PERSONS

The individuals listed in this section are designated as Key Persons for this engagement. These personnel are essential to the success of the project due to their responsibilities, specialized skills, and expected availability. Any substitution of a Key Person must be approved in writing by the State. The State may require a replacement if performance does not meet expectations. Any proposed replacement must meet or exceed the qualifications of the original individual. The State may interview proposed replacements before approval.

Executive Lead

The Executive Lead directs overall project oversight and serves as a senior liaison with ISP and other State stakeholders. This individual ensures that the Vendor assigns adequate and qualified staffing to support delivery and addresses issues that require executive attention. The person filling this role will have at least seven (7) years of experience managing or leading projects of similar size and scope. The individual will also have at least three (3) years of experience with the proposed solution or with a system of similar capabilities. Experience implementing the proposed AFIS for at least one client is preferred.

Project Manager

The Project Manager coordinates all design, development, and implementation activities. This person serves as the single point of contact for all system related communications between the Vendor and the State. The Project Manager ensures performance standards are met and that deliverables are completed on schedule. This role is full time during design, development, implementation, and stabilization. On-site presence will be provided as required by ISP. The individual who fills this position will have at least seven (7) years of experience managing large-scale information technology projects and at least three (3) years of experience with the proposed solution or a system of similar size. A minimum of five (5) years of experience with system design, development, implementation, maintenance, and operations is expected. Project management certification is preferred. Strong written and verbal communication skills are required.

Lead Solution Architect

The Lead Solution Architect guides architectural design activities and ensures alignment of the solution with required technical standards. Responsibilities include leading system and subsystem design, application and data modeling, systems integration activities, and the review of technical documentation. This individual must have at least three (3) years of experience developing web applications and at least three (3) years of experience managing system architecture or system development projects. Experience with the proposed solution or with a system of similar capabilities is preferred. Availability from project start through system go live is required.

Lead Business Architect

The Lead Business Architect guides process design and ensures that system capabilities align with business requirements. Responsibilities include documenting business processes, identifying opportunities to reduce customization through configuration, and overseeing development of operational procedures. This individual must have at least three (3) years of experience leading business process design and at least three (3) years of experience managing business system development efforts. Experience with the proposed solution or a system of similar capabilities is preferred. Availability from project start through system go live is required.

Implementation Lead

The Implementation Lead is responsible for overseeing implementation activities, tracking performance standards, and addressing escalated issues during deployment. The position is full time through implementation planning and execution. This individual must have at least three (3) years of experience with the proposed solution or a system of similar size and at least two (2) years of experience managing implementation activities for web-based applications. Prior experience implementing the proposed solution for another client is preferred.

Testing Lead

The Testing Lead directs all testing activities including planning, documentation, scheduling, and execution. Responsibilities include coordination with all testing participants, oversight of defect tracking, and support for user acceptance testing. This individual ensures compliance with State and Federal testing requirements. Full-time support is required during system testing. The Testing Lead must have at least five (5) years of experience leading testing efforts for complex projects and at least three (3) years of experience performing various testing cycles.

Data Migration Lead

The Data Migration Lead oversees data extraction, profiling, mapping, transformation, migration, and validation. This individual ensures migrated data is accurate, complete, and compliant with State requirements. Responsibilities include developing the data migration strategy, ensuring the data migration plan is complete and accurate initially and throughout the project, coordinating data profiling and cleansing, overseeing data mapping and conversion design, directing migration tool and script development, and ensuring overall data quality. The role requires close coordination with State data owners, technical teams, and business stakeholders to resolve data issues and ensure migration deliverables meet standards. This position requires full‑time engagement during data design, migration development, mock conversions, testing, cutover, and Hypercare. The individual will have at least five (5) years of experience leading data migration efforts for large‑scale IT projects and at least three (3) years of experience with data migration for the proposed solution or a similar system. Experience with data profiling, data quality management, and migration automation tools is required. Prior experience completing a full data conversion for the proposed solution for another client is preferred.

Release Manager

The Release Manager works with the State to develop the release strategy and manages all planned post implementation releases. Responsibilities include maintaining the release plan and supporting release activities for statewide rollout. This individual will have at least three (3) years of experience with the proposed solution or with a system of similar capabilities and at least two (2) years of release management experience. Experience supporting releases for the proposed solution for other clients is preferred.

## OTHER PROJECT STAFF

The Vendor will assign sufficient staff with the skills and experience required to support successful delivery of the project. These personnel will work under the direction of the Key Persons and will perform activities needed to complete design, development, testing, deployment, and operations support. The Vendor will prepare a Project Resource Staffing Plan that identifies all project staff, their roles and responsibilities, and the qualifications required for each position. The Staffing Plan will also describe the work locations of project personnel and any arrangements that include remote work when approved by the State.

The Vendor will ensure that all project staff meet the minimum qualifications defined by the Vendor’s proposed solution and by the expectations of the State. The Vendor will also ensure that staff receive any required training to perform their duties and maintain compliance with State policies. This includes training needed for quality standards, security requirements, and operational processes.

The State reserves the right to review proposed staff and to request a change if performance does not meet expectations or if the individual’s skills are not aligned with the work required. The State may interview proposed replacements before approval. Any replacement staff must meet or exceed the qualifications of the original assigned individual.

The Vendor will maintain appropriate staffing levels throughout the engagement and will provide timely replacements for staff who depart or are reassigned. The Vendor will follow the timelines established for staff replacement and will ensure that any transition of duties is completed without disruption to ongoing work. Staff providing services under this engagement must be located within the United States unless the State grants written approval for an exception.

The Vendor will ensure that all personnel who require access to Criminal Justice Information meet all State and Federal security requirements. The Vendor will sign the CJIS Security Addendum at the corporate level and each employee who requires unescorted access to Criminal Justice Information will sign the CJIS Security Addendum Certificate. Each employee with access to Criminal Justice Information will also complete annual CJIS Awareness Training through the CJISONLINE portal. Individuals who do not meet these requirements will not be permitted to work on the project.

The Vendor will maintain low turnover among project staff and will describe in the Staffing Plan how workforce stability will be supported. This includes strategies to retain high performing staff and to ensure continuity of knowledge throughout the contract term.

Complete Attachment Q - Resource Usage Matrix to provide the roles and associated number of hours the Respondent expects to commit to the project, which should include both Key Persons and Other Project Staff sections, and the roles and associated number of hours estimated for the State resources. These amounts should be based on the functionality the State desires, included in this RFP.

## DOCUMENT MANAGEMENT

The State will establish a project repository using Microsoft Teams that will serve as the primary location for all documents created or exchanged during the engagement. The Vendor will use the State provided repository for all deliverables, project artifacts, administrative documents, and supporting materials. The Vendor will submit all documents in both editable and PDF formats. Documents will follow the naming conventions and version control standards established by the State.

The Vendor will maintain version history for all project documents. This includes tracking updates, revisions, approvals, and the status of each document. The Vendor will ensure that documents remain organized, current, and easily accessible to State staff at all times. The Vendor will not use external or unapproved repositories for project work. All documentation must reside in the State approved environment.

The preference is for the Vendor to use the State’s Application Lifecycle Management tools such as Azure Dev Ops (ADO) for managing requirements, design artifacts, testing artifacts, and release information. These tools will also be used to track versioning, traceability, approvals, and the lifecycle of design and development tasks. The Vendor will follow all State standards for documentation quality and will ensure that each artifact is complete and consistent with earlier and later project phases.

The Vendor will ensure that all documentation remains accurate throughout the life of the project. When changes to requirements, design, testing, or implementation occur, the Vendor will update the associated documentation in a timely manner. As part of deliverable acceptance, the Vendor will ensure that all documentation associated with that deliverable is complete and stored in the project repository.

## STATUS UPDATES AND REPORTING

The Vendor will provide regular and timely reporting to support transparency, oversight, and decision making throughout the project. Reporting will follow the structure described in this section and will use formats approved by the State. The Vendor will revise reporting templates at the request of the State.

Weekly Status Reports

The Vendor will submit a weekly status report that provides a clear view of project progress and any conditions that require State attention. Each weekly status report will include the items listed below.

- A summary of work completed

- A summary of work planned for the next reporting period

- Schedule compliance, including any changes to the critical path

- Status of open incidents, including priority levels and the length of time each incident has remained open

- Status of open defects, including severity levels and the length of time each defect has remained open

- Current risks with mitigation actions

- Current issues and required decisions

- Updates to the project schedule when required

- Open action items

Every-Other-Week Review Meetings
The Vendor will schedule and own review meetings with the State every other week. These meetings will provide a consolidated view of project performance, staffing levels, progress against deliverables, and any emerging risks or issues. The Vendor will prepare all necessary materials for these meetings, including sending out an agenda no less than 24 hours prior to the start of the meeting and will update documentation as requested by the State. The Vendor will capture and disseminate meeting minutes no later than 24 hours after the conclusion of the meeting. Meeting frequency may increase as the project approaches implementation.

Quarterly Business Reviews

The Vendor will schedule and own quarterly business reviews that summarize work completed during the period, planned work for the upcoming quarter, and performance across key indicators. The Vendor will prepare all necessary materials for these meetings, including sending out an agenda no less than 24 hours prior to the start of the meeting. The review will include analysis of trends in incidents, defects, risks, schedule adherence, and deliverable acceptance. The Vendor will provide updated dashboards or summary materials for these sessions. The Vendor will capture and disseminate meeting minutes no later than 24 hours after the conclusion of the meeting. These meetings may become more frequent as the project approach implementation.

Ad Hoc Meetings

The Vendor will attend ad hoc meetings when requested by the State. When on site attendance is required, the State will provide three business days’ notice. When presentation materials are needed, the Vendor will prepare the materials and provide them to the State in advance of the meeting.

Documentation of Reporting and Records

All reports, meeting materials, decision logs, dashboards, and supporting documents will be stored in the State designated project repository. The Vendor will maintain version control, ensure information is accurate, and update records in a timely manner.

## ORGANIZATIONAL CHANGE MANAGEMENT (OCM)

The objective of the Organizational Change Management (OCM) activities is to plan, develop, and execute a comprehensive OCM Plan that supports successful implementation and user adoption of the AFIS solution. OCM activities shall include, but are not limited to, conducting an Organizational Change Readiness Assessment, developing and maintaining a Stakeholder Communication Plan, creating Organizational Transition Plans, and facilitating overall stakeholder engagement and “buy‑in.”

OCM efforts will occur within the ISP as well as with external entities whose use of the AFIS solution as mandated by statute. These activities require disciplined planning, coordination, and communication to ensure efficient implementation, operational readiness, and broad user acceptance. OCM tasks are typically integrated into, or aligned with, the overall implementation and must be coordinated with project management, system integration, training, and deployment activities to ensure a seamless transition to the future‑state environment.

# INDEPENDENT VERIFICATION AND VALIDATION

If the State decides to add Independent Verification & Validation (IV&V) services as part of this Contract, the Vendor will copy the Indiana Department of Administration (IDOA) – IV&V Team member(s) on all project related communications (emails, meeting invites, collaboration tools, etc.) and will grant access to all documents and deliverables throughout the term of the Contract.  If IDOA elects to deploy IV&V services in connection with this engagement, the IV&V Team will review and assess all deliverables to determine compliance with the State’s requirements set forth in the Contract including the Statement of Work. For contracts entered into, renewed, or amended after June 30, 2026, the IV&V Team may serve as an approving authority, and if the IV&V Team is the approving authority, no payment shall be issued to the Vendor unless and until IV&V has provided such approval.

# COMPLIANCE REQUIREMENTS

## SECURITY POLICIES AND STANDARDS

The State has robust and comprehensive security standards that permeate all levels of the organization. The Indiana Office of Technology (IOT) has been tasked with establishing and maintaining these security standards. The security standards include assessing security risks, developing, and implementing effective security procedures, and monitoring the effectiveness of those procedures. If the proposed solution involves information technology-related products or services, all such products or services are to be compatible with any of the technology standards found in the Statewide IT Policies, Procedures, & Standards (https://www.in.gov/iot/policies-procedures-and-standards/) that are applicable, including the assistive technology standard.  The Contractor will be required to sign a Non-Disclosure Agreement (NDA) to access the more sensitive standards and policies.  The Contractor should review the Statewide IT Policies, Procedures, & Standards and ensure their proposed solution meets all standards therein.

Any proposed cloud-based service offerings submitted in response to this RFP will need to comply at the time of solution implementation with the IOT RAMP Policy for Cloud Offerings (Policy P.05), which can be found at https://www.in.gov/iot/iot-vendor-engagement/. Prospective vendors should keep all the foregoing in mind as they prepare their proposals and be confident that any proposal they ultimately choose to submit are flexible enough to accommodate commonly accepted industry practices and standards in the typical state government-required RAMP. Please visit the RAMP Cybersecurity Frequently Asked Questions page for additional information.

## ARTIFICIAL INTELLIGENCE STANDARDS

The State has adopted an enterprise-level policy governing the use of Artificial Intelligence (AI) within state government. The State’s AI Policy is issued and monitored by the Office of the Chief Data Officer (OCDO), in cooperation with the Chief Privacy Officer (CPO) and the Management Performance Hub (MPH). As a complement to the AI Policy, the State Agency Artificial Intelligence Systems Standard outlines the rationale behind the AI Readiness Assessment Process required for the implementation or any use of AI by a state agency. That Standard outlines the requirement for the submission of a Readiness Assessment Questionnaire prior to implementation or use of an AI tool or system. Any proposed solution meeting these requirements must support the State’s AI Policy and follow the AI Readiness Assessment Process. See https://www.in.gov/mph/AI/ for more detailed information.

## ACCESSIBILITY

In accordance with Indiana Code § 4-13.1-3 and the IN.gov Accessibility Policy, all systems must comply with the Web Content Accessibility Guidelines (WCAG) 2.1, ensuring that digital services are usable by individuals with disabilities, including those using assistive technologies. Any deviation from these requirements must be approved in writing by IOT in advance.

## DATA EXCHANGE

The State has robust and comprehensive data transmission standards that operate enterprise wide. The IOT established and maintains these standards, which support IOT’s data exchange and API-led strategies for the State. The Vendor’s solution must support the State’s standard API and file transfer methods to facilitate secure data transmission. The State’s standardized data transmission technologies are the MuleSoft API Management and GoAnywhere Managed File Transfer (MFT) services. See https://www.in.gov/iot/policies-procedures-and-standards/applications-standards/.

## AUTHENTICATION

The proposed solution is expected to integrate with Access Indiana. The IN.gov Program is tasked with implementing a single sign-on authentication mechanism and Identity Provider for online applications for the State of Indiana, referred to as Access Indiana. The benefits of a standard authentication solution, integration strategy, integration process, and more can be found at Access Indiana Authentication (https://www.in.gov/inwp/applications/authentication/).

# KEY PERFORMANCE INDICATORS (KPIs)

The State will use Key Performance Indicators (KPIs) to measure performance and outcomes of the Contract. The specific KPIs and their targets will be defined and agreed upon by the State and the Vendor during the initial phases of the requirements under the Contract. At a minimum, on time delivery at quality standards of the scope provided within the budget set forth in the Contract will each be measured.  Additionally, the State will collect a modified Net Promoter Score from customers to this Contract in its discretion.  Low ratings on the modified Net Promoter Score or failure to meet any other KPIs may be deemed, at the discretion of the State, to constitute default under the Contract.

If the Vendor does not meet agreed upon Key Performance Indicator targets, the State may require the Vendor to provide a corrective action plan within the timeframe defined by the State. Continued failure to meet Key Performance Indicators after corrective actions are implemented may result in the withholding of payments or may result in contract termination according to the terms of the contract.

# MAINTENANCE AND OPERATIONS (M&O)

The Vendor will provide Maintenance and Operations services for the system after implementation. These services will support the stability, performance, and ongoing functionality of the system for all users. The Vendor will provide staffing, processes, monitoring, and support activities needed to sustain operations and meet the requirements defined by the State. The Vendor will maintain all services at the performance levels required in the contract and described in the Service Levels and Performance Remedies section.

Infrastructure Management

The Vendor will maintain the system infrastructure and tools that support operational use of the solution. This includes resolving functional issues, applying patches, performing preventative maintenance, planning and completing upgrades, and monitoring performance. The Vendor will work with State information technology teams to support the infrastructure environment and ensure alignment with State standards.

Application Monitoring and Support

The Vendor will monitor all system components to ensure availability and performance. Monitoring will identify issues that affect system functionality and will support timely response and resolution. The Vendor will follow established escalation procedures and will meet the response and resolution expectations defined by the State. The Vendor will support incident and problem management activities and will work to minimize recurring issues.

Incident Management

The Vendor will log, track, and resolve incidents using State approved tools and processes. The Vendor will identify incident trends, perform root cause analysis, and implement corrective actions to prevent recurrence. The Vendor will keep the State informed of all incidents and will provide timely updates based on priority levels. Incident reporting will be included in weekly status reports.

Access Management

The Vendor will assist the State in defining user roles and security profiles needed for the system. This includes creating new roles, monitoring access, and supporting user account changes. The Vendor will maintain user access in alignment with State security standards and will work with the State to adjust access when needed.

Data Warehouse and Data Management Support

The Vendor will support data warehouse, operational data store, and data mart needs that relate to reporting and analytical activities. This includes managing data subsets, supporting summarized data views, and working with State staff on the use of development and production databases.

Batch Processing

The Vendor will support configuration and operation of batch processes that are needed to maintain system functions and data processing workflows.

Application Lifecycle Management Support

The Vendor will maintain all source code, requirements, design documents, and testing artifacts within the State’s Application Lifecycle Management tools. This includes managing configurations and build information according to State standards.

Technical Support and Routine Maintenance

The Vendor will resolve system defects, complete routine maintenance activities, and maintain system performance. Routine maintenance activities that do not change performance levels or reduce capacity are included in the contracted services and will be provided at no additional cost to the State. Examples include updates required for Federal or State compliance, updates to tables, and changes related to reporting frequency or format.

Hypercare Support

Immediately following system implementation, the Vendor will offer at least 60 calendar days of Hypercare support, or until both the State and Vendor agree to end it, to ensure a smooth transition to operations. Hypercare will include real time monitoring, rapid response to issues, and dedicated support for State staff.

Quarterly Business Reviews

The Vendor will schedule and own quarterly business reviews that summarize work completed during the period, planned work for the upcoming quarter, and performance across mutually agreed upon key indicators. The Vendor will prepare all necessary materials for these meetings, including sending out an agenda no less than 24 hours prior to the start of the meeting. The Vendor will capture and disseminate meeting minutes no later than 24 hours after the conclusion of the meeting. Each quarterly business review during the operations period shall include a summary of work completed during the previous quarter, including major milestones, deliverables, and resolved issues. The review will also cover planned work and upcoming initiatives for the next quarter, detailing objectives, timelines, and anticipated challenges. Furthermore, it will assess performance against key indicators such as system uptime, defect resolution, user satisfaction, and compliance with Federal and State requirements. The discussion will encompass routine maintenance activities performed, including updates for compliance, changes to tables, and modifications related to reporting frequency or format. Outstanding issues, risks, and recommended mitigation strategies will be identified. Finally, opportunities for process improvement, innovation, and feedback from State stakeholders will be explored.

# END OF CONTRACT TRANSITION AND TURNOVER

If a transition is needed from the incumbent vendor, the Vendor, with the support of the State, shall be responsible for attending and/or conducting knowledge transfer sessions with the incumbent vendor to ensure all AFIS functionality is transitioned smoothly without interruption to stakeholders.

The State seeks to ensure that program stakeholders experience no adverse impact from the transfer of the M&O and enhancement services to either the State or to a successor Vendor when the Contract is complete or terminated early. These services must be continued without interruption, and the Vendor must support the State and any successor vendor in transition efforts during the Contract term. The dates and data requirements in the following sections do not limit or restrict the State's ability to require additional information from the Vendor or modify or shorten the turnover schedule as necessary.

| Months from Contract End | Deliverables |
| --- | --- |
| 12 | - State-approved Turnover Plan covering the possible turnover of the system or operational activities to either the State or a successor vendor. The Turnover Plan must be a comprehensive document detailing the proposed schedule and activities associated with the turnover tasks outlined in the sections below. The Turnover Plan shall describe the Vendor's approach and schedule for transfer of inventories, code/logic, training materials, SDLC artifacts, correspondence, documentation of outstanding issues, and operational support information to a repository of the State’s choosing. Further, the Turnover Plan must clarify what in-progress M&O and Enhancement activities will be applicable during the Turnover and how to transition those items to the State and the new Contract. - Begin implementation of Turnover Plan. |
| 9 | - The Vendor shall appoint, with State approval, a Turnover Manager who will manage and coordinate all Turnover activities. The Turnover Manager may be an individual already staffed on the project. The Vendor shall submit their Turnover Manager's qualifications as part of their Turnover Plan. The Vendor shall not reduce operational staffing levels during the turnover period without prior approval by the State. - Store on the State’s selected repository: - A copy of non-proprietary systems and database(s) used. - All solution and solution documentation (requirements, design, BPMs, user interface (UI) specs, form specs, technical specifications, technical configurations, SDLC artifacts, architecture documents, test artifacts, security artifacts, database information (conceptual, physical, and logical data models) and project management documentation. - Location of logs and infrastructure configuration details for load balancing used during the Contract to ensure compliance with operational requirements. - Other documentation includes, but not limited to, user, provider, and operations manuals, and documentation of any interfaces developed to support business activities between the Vendor and other parties. - Clarity must be provided on whether each artifact is historical or currently applicable. The Vendor must also provide for all artifacts an indication of whether they are currently in production, non-production, pending implementation, and/or no longer in production. This requirement applies for both the items within the scope of M&O as well as any in-progress SDLC artifacts and solution components. - The Vendor will provide documentation for any outstanding issues, including known root causes, impacts, and recommended resolution steps. |
| 5 | - Begin training State staff or successor vendor staff, in the operations and procedures performed by Vendor staff. - Begin working with the State and the successor vendor on major and minor releases. - Support shadowing by the State and successor vendors for M&O and Enhancement activities. |
| 2 | - Complete training of State staff or successor vendor’s staff. - Transition of services to the State staff or successor vendor. - Provide support as requested by the State in all aspects of the non-production and production releases at this time to ensure that no interruption in services occurs. This support will be invoiced according to the contractual hourly rates. - Ensure that full administrative, edit access is provided to appropriate staff under the successor vendor. |

As part of the Contract Turnover responsibilities, the following shall apply:

- The Vendor will not reduce operational staffing levels during the turnover period without written approval from the State. This requirement applies to all personnel who support ongoing Maintenance and Operations activities as well as personnel responsible for turnover tasks.

- Provide to the State, or its agent, within fifteen (15) business days of requesting all updated data and reference files, scripts, and all other documentation and records as required by the State or its agent.

- Appoint, with State approval, a Turnover Manager with at least one (1) year of recent IT system experience to manage and coordinate all End of Contract Turnover activities. The Vendor shall submit their proposed individual’s qualifications as part of their Turnover Plan. The Vendor shall not reduce operational staffing levels during the Turnover period without prior approval by the State.

- Do not in any way restrict or prevent Vendor staff from accepting employment with any successor vendor. The State will work with the incumbent and successor vendors at the timing of any transition of incumbent staff.

- If the optional Contract terms are exercised during Turnover activities, these activities shall shift to the next year. If the Turnover is halted due to the State exercising an optional term extension, invoices will not include Turnover Manager costs after the State's date to halt Turnover activities until those activities resume (with the State's approval) in the following year.

- Any Turnover costs shall be covered by the M&O fees.

- If the State exercises an optional contract extension year during turnover, turnover activities will pause and resume on the schedule aligned to the updated contract end date. Turnover Manager costs will not accrue during any pause unless the State authorizes otherwise.

- By the end date of the Contract, the Vendor must turn over all State property to the State, and Vendor’s access to all State infrastructure and facilities will be terminated.

# SERVICE LEVELS AND PERFORMANCE REMEDIES

The Vendor will meet the service levels defined in this section for the duration of the contract. Service levels represent the minimum performance expectations for availability, responsiveness, quality, and operational support. The State may revise service levels at any time with written notice when operational needs or policy requirements change. Service level performance will be reviewed as part of weekly status reporting, monthly reviews, and quarterly business reviews.

Performance against these service levels will be used to assess compliance with contract obligations and will be considered in determining whether the Vendor has met Key Performance Indicator expectations.

Definitions for Business Hours. Business Days, and Calendar Days

Business Hours: Business hours are defined as 8:00 AM to 5:00 PM Eastern Time, Monday through Friday, excluding State-recognized holidays. Support activities specified as "business hours" must occur within this window.

Business Days: A business day is any day Monday through Friday, excluding weekends and all State-recognized holidays. Resolution times measured in "business days" begin on the next business day following incident logging unless otherwise specified.

Calendar Days: A calendar day includes all days of the week, including weekends and holidays. Unless otherwise specified, timeframes measured in calendar days run continuously without pause, beginning immediately at the time an incident, milestone, or contractual requirement is triggered.

## SYSTEM AVAILABILITY

The Vendor shall provide a hosted, managed application with a 99.9% system availability as measured over a rolling 30‑day period, excluding scheduled maintenance windows. Availability shall be calculated as the percentage of time the application is accessible and operational during the measurement period.

The State defines AFIS as State-level Critical, where it meets criteria as CORE INFRASTRUCTURE and/or “EO-critical Software” as outlined in Presidential EO 14028 (Definition of Critical Software Under Executive Order (EO) 14028).

Scheduled maintenance windows (e.g., patching, upgrades, configuration changes) shall be excluded from the 99.9% availability calculation. The Vendor shall provide a written schedule of all planned maintenance, including the expected duration of each window, and deliver a monthly update to the State, submitted no later than the fifteenth (15) business day of each month, outlining all planned maintenance activities for the upcoming six months with anticipated dates and durations for each window. Scheduled maintenance must be approved by the State no later than 72 hours in advance and must occur outside of peak operating hours unless the State gives written approval.

If the Vendor fails to meet the 99.9% availability target, the Vendor will incur penalties as outlined in the Liquidated Damages and Performance Enforcement section.

The vendor shall provide evidence of up-time monitoring, including logs, reports, and third-party verification, for each month of the contract term. Reports shall be available to the customer within 15 business days of the end of each month.

## DISASTER RECOVERY

Vendors must provide documented evidence demonstrating that they conduct Disaster Recovery (DR) testing on a basis agreed upon by all parties. Evidence may include DR test reports, executive summaries, remediation follow-up plans, or third-party audit attestations. The required frequency of DR testing will be determined by the issuing organization and communicated during the contract negotiation phase. Vendor agrees to maintain this testing cadence throughout the contract term and make reports available upon request.

## INCIDENT RESPONSE AND RESOLUTION

The Vendor will acknowledge and resolve incidents within the timeframes listed below. Priority levels will be assigned by the State.

Priority Levels and Required Service Timeframes

P1 – Critical Outage (Full System Down / Core Business Halted)

- Initial Response: 15 minutes (24x7)

- Restoration Time: 1 hour (24x7)

P2 – Significant Degradation (Major Function Impaired; No Workaround)

- Initial Response: 30 minutes (business hours or 24x7 per contract)

- Restoration Time: 4 business hours

P3 – Partial Function Loss With Workaround

- Initial Response: 4 business hours

- Restoration Time: 2 business days

P4 – Minor Defect or Cosmetic Issue

- Initial Response: 1 business day

- Resolution Time: 5 business days

Communication Requirements

The Vendor must:

- Provide ongoing updates at intervals agreed upon by the State.

- Escalate unresolved P1 issues internally within 30 minutes.

- Provide a written Post-Incident Report for all P1 and P2 incidents within five business days, including root cause and corrective actions.

- Maintain a 24x7 emergency contact method for P1 incidents.

Status Reporting

Incident status and resolution progress must appear in the Vendor’s weekly status report, including:

- All open incidents with assigned priority

- Current status and estimated resolution time

- Any SLA breaches from the prior week

- Summary of root causes and recurring issues

## DEFECT RESOLUTION (POST GO-LIVE)

The Vendor will resolve defects discovered after go-live within the timeframes listed below. Severity levels will be assigned by the State.

- Critical defects: resolve within one hour

- High severity defects: resolve within one business day

- Medium severity defects: resolve within three business days

- Low severity defects: resolve within one week

## REPORTING REQUIREMENTS

The Vendor will prepare and submit monthly reports that describe service level compliance. At a minimum, the report will contain:

- System availability statistics

- A list of incidents with response and resolution times

- Open and closed defects

- Root cause analyses for any service level failures and a corrective action plan to reduce future failures

- A summary of trends in incidents, defects, or outages

## LIQUIDATED DAMAGES AND PERFORMANCE ENFORCEMENT

Service level failures may result in liquidated damages or financial credits as described below.

Availability Credits: Provided from the Vendor to the State

- 99.0% – 99.89% availability: 5% credit of the monthly service fee

- 98.0% – 98.99% availability: 10% credit of the monthly service fee

- Below 98.0% availability: 20% credit of the monthly service fee

  - If availability falls below 98% for two consecutive months, the State may require a formal remediation plan or may pursue contractual remedies, including termination.

Missed Milestones

If a project milestone is delayed beyond the approved and mutually agreed-upon project schedule due to Vendor action or inaction, the following liquidated damages shall apply:

- $1,000 per calendar day, beginning the day after the missed milestone date.

- Damages accrue until the milestone is completed and accepted by the State.

- Total milestone-related damages will not exceed 10% of the total contract value unless otherwise negotiated.

SLA Violations

For every SLA violation, the State may take one or more of the actions listed below.

- Require a corrective action plan

- Withhold payment

- Reduce payment for affected deliverables

- Initiate contract termination for cause

Staffing Noncompliance

If any Vital Personnel position remains unfilled beyond the contractual replacement window, the Vendor will owe five hundred dollars per day until the position is filled with an approved individual.