## Inactive Projects
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Auth Date | FMIS Balance | PO Unliquidated | Inactive Days | Last Action Date | Fund Sponsor | Open POs | PCO Des Status | PCO Task ID
1173626 | R-35296 | Crawfordsville | Tippecanoe | Lafayette - West Lafayette | N/A | Tippecanoe County | Klondike Road (CR 300W) from Lindberg Rd.(CR 200N) to US 52 in Tippecanoe Co. | 2021-07-23 07:16 | 2018-03-14 | 2018-03-14 | 2013-07-21 | 70280.14 | 4043.35 | 312 | 2022-01-07 16:22 | Local (MPO) | 0020050542 [CN] | TR | #N/A
1801364 | N/A | Crawfordsville | Vigo | Terre Haute | N/A | MPO - Terre Haute | Terre Haute MPO Unified Work Program UPWP, PL & HSIP for FY 2019-2020 | 2021-02-19 07:32 | N/A | N/A | 2018-06-28 | 61158.2 | 61158.2 | 466 | 2021-05-13 15:01 | Local (MPO) | 0020044242 [PL] | TR | 105959
1801265 | N/A | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Beaver Lane at NS RR DOT # 510019A in Goshen | N/A | N/A | N/A | 2019-05-07 | 703863 | 782070 | 1120 | 2022-04-21 14:09 | Local (MPO) | 0020084145 [RR] | TR | #N/A
1900391 | N/A | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Madison St. at NS RR DOT 510039L in Goshen | N/A | N/A | N/A | 2020-01-23 | 425390.4 | 472656 | 859 | 2022-04-21 14:09 | Local (MPO) | 0020084146 [RR] | TR | #N/A
1400944 | B-37591 | Greenfield | Marion | Indianapolis | N/A | Indianapolis | Monon Bicycle/Pedestrian Bridge over 38th Str.28 miles E of 38th & College | 2020-10-23 07:31 | 2020-01-15 | 2020-01-15 | 2019-11-26 | 0 | 892.75 | 585 | 2021-05-03 12:43 | Local (MPO) | 0020036255 [CN] | TR | #N/A
1401701 | R-38073 | Greenfield | Hamilton | Indianapolis | N/A | Hamilton County | 146th St, 1000' W Hamilton / Boone Co Line to 1000' W of Shelborne Rd | 2021-04-23 07:37 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 0 | 68787.27 | 403 | 2021-04-23 07:37 | Local (MPO) | 0020036968 [CN] | TR | #N/A
1401719 | B-38039 | Greenfield | Marion | Indianapolis | N/A | Indianapolis | 38th St Bridge (#2001F) over CSX RR; betw Arlington Ave. & Massachusetts Ave | 2021-05-21 07:11 | 2018-11-15 | 2018-11-15 | 2018-09-17 | 0 | 62154.85 | 375 | 2021-05-21 07:11 | Local (MPO) | 0020056808 [RR] | TR | #N/A
1401730 | R-38048 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Intersection of Combs Road and Stop 11 Road | 2021-05-21 07:11 | 2019-09-11 | 2019-09-11 | 2019-07-24 | 15356.88 | 14618.77 | 375 | 2021-05-21 07:11 | Local (MPO) | 0020083492 [CE] | TR | #N/A
1500286 | N/A | Greenfield | Madison | Not Applicable | N/A | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-04-02 07:14 | N/A | N/A | 2018-07-30 | 4484.6 | 4484.6 | 424 | 2021-07-27 11:07 | Local (Non-MPO) | 0020046599 [PE] | TR | #N/A
1600971 | R-40327 | Greenfield | Tipton | Not Applicable | Windfall (1561) | Windfall | SW and ADA Upgrades on SR 213 - Sherman Str and Grant St in Windfall | 2021-05-07 08:10 | N/A | 2025-07-09 | 2017-10-30 | 4682.37 | 4682.37 | 389 | 2021-05-07 08:10 | Local (Non-MPO) | 0018806979 [PE] | TR | #N/A
1600972 | R-40320 | Greenfield | Jay | Not Applicable | Redkey (1426) | Redkey | Town Park Sidewalk in Redkey | 2021-06-14 12:06 | N/A | 2022-07-13 | 2017-12-08 | 6797.18 | 6797.18 | 351 | 2021-06-14 12:06 | Local (Non-MPO) | 0018809394 [PE] | TR | #N/A
1600974 | R-40321 | Greenfield | Jay | Not Applicable | Dunkirk (1133) | Dunkirk | Highland Ave - W Jay Middle School to Speedcat Alley | 2021-07-30 09:10 | N/A | 2022-07-13 | 2017-11-16 | 3345.62 | 3345.62 | 305 | 2021-07-30 09:10 | Local (Non-MPO) | 0018808249 [PE] | TR | #N/A
1700722 | R-40282 | Greenfield | Hamilton | Indianapolis | Fishers (1162) | Fishers | Intersection Improvement roundabout at Southeastern Pkwy & Cyntheanne Rd | 2021-07-30 09:10 | 2021-11-17 | 2021-11-17 | 2018-04-03 | 2081270.49 | 2455852.39 | 305 | 2021-12-28 12:55 | Local (MPO) | 0020076641 [CN] | TR | #N/A
1700936 | T-40371 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Safe Routes to Transit - South | N/A | 2021-09-15 | 2021-09-15 | 2021-08-12 | 2660320 | 2186392.34 | 292 | 2022-05-25 07:54 | Local (MPO) | 0020070533 [CE]; 0020074264 [CN]; 0020074265 [CN] | TR | #N/A
1801218 | N/A | Greenfield | Madison | Anderson | N/A | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2021-07-30 09:10 | N/A | N/A | 2018-06-28 | 62388.43 | 3299.45 | 305 | 2022-03-02 15:33 | Local (MPO) | 0020022816 [PL] | TR | 105237
1593056 | N/A | LaPorte | St. Joseph | Not Applicable | N/A | St. Joseph County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2021-03-05 07:20 | N/A | N/A | 2020-07-23 | 67729.78 | 67729.78 | 452 | 2021-07-23 15:36 | Local (Non-MPO) | 0020045720 [PE] | TR | #N/A
1702152 | R-37496 | LaPorte | St. Joseph | South Bend (MI) | N/A | St. Joseph County | Douglas Road over Juday Creek Bridge #191 | N/A | 2020-12-09 | 2020-12-09 | 2020-11-09 | 846463.24 | 1058079.05 | 568 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | TR | #N/A
1702153 | R-37496 | LaPorte | St. Joseph | South Bend (MI) | N/A | St. Joseph County | Ironwood Road over Juday Creek Bridge #192 | N/A | 2020-12-09 | 2020-12-09 | 2020-11-09 | 842706.93 | 1053383.66 | 568 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | TR | #N/A
1801738 | R-41770 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Gary (1182) | Gary | Complete Streets Enhancements on Lake Street and minor on US 12/20 in Gary | N/A | 2021-05-05 | 2021-05-05 | 2018-09-04 | 1824016.01 | 2819627.08 | 1365 | 2021-06-01 15:13 | Local (MPO) | 0020056309 [PE]; 0020063648 [CE]; 0020064507 [CN] | TR | #N/A
901275 | R-36161 | Seymour | Floyd | Louisville (KY)-IN | N/A | New Albany | Upgrade Market and Spring Streets as 2-way streets from IN 111 to State St | 2021-04-02 07:14 | 2017-03-01 | 2017-03-01 | 2015-04-20 | 66754.79 | 56097.26 | 424 | 2021-04-02 07:14 | Local (MPO) | 0017817671 [RR] | TR | #N/A
1400619 | N/A | Seymour | Harrison | Not Applicable | N/A | Indiana Department of Transportation | Angel Run Road at NS DOT# 724987K near Crandall | 2020-07-24 07:29 | N/A | N/A | 2016-04-25 | 485595.97 | 485595.97 | 676 | 2022-05-04 13:37 | Local (Non-MPO) | 0020084743 [RR] | TR | #N/A
1500208 | PLC-38178 | Seymour | Jefferson | Not Applicable | N/A | Jefferson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-07-02 07:21 | N/A | N/A | 2018-10-22 | 10568.06 | 10568.06 | 333 | 2021-09-17 09:34 | Local (Non-MPO) | 0020007472 [PE] | TR | #N/A
1600655 | R-40224 | Seymour | Johnson | Indianapolis | Franklin (1173) | Franklin | S Main St from S Main Bridge at Young's Creek to US 31 | 2020-12-11 07:29 | 2019-11-14 | 2019-11-14 | 2019-10-08 | 0 | 28855.27 | 536 | 2020-12-11 07:29 | Local (MPO) | 0020033019 [CN] | TR | 105906
1700735 | R-40293 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | From existing B-Line Trail terminus at Adams Street to 17th at Crescent | N/A | N/A | 2022-11-16 | 2021-05-05 | 717640 | 717640 | 391 | 2021-05-05 09:52 | Local (MPO) | 0020063657 [ROW] | TR | #N/A
1700976 | R-40337 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | Systematic safety improvements expected to include approximately 25 crosswalks. | N/A | 2022-04-06 | 2022-04-06 | 2021-02-22 | 495542.71 | 682293.42 | 463 | 2022-05-09 14:12 | Local (MPO) | 0020076879 [CE]; 0020085465 [CN] | TR | #N/A
1801245 | N/A | Seymour | Monroe | Bloomington | N/A | MPO - Bloomington | Bloomington MPO UPWP for FY 2019-2020 | 2020-12-28 07:22 | N/A | N/A | 2018-06-28 | 93864.56 | 61075.13 | 519 | 2020-12-28 07:22 | Local (MPO) | 0020021893 [PL] | TR | 105124
1802886 | R-41919 | Seymour | Jefferson | Not Applicable | Madison (1295) | Madison | Wilson Avenue, between Industrial Drive/Scott Court and Hutchinson Lane (aka JA | N/A | N/A | 2023-07-12 | 2021-08-13 | 352240 | 352240 | 291 | 2021-08-13 12:13 | Local (Non-MPO) | 0020068690 [ROW] | TR | #N/A
1902078 | N/A | Seymour | Brown | Not Applicable | N/A | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2021-2024 | N/A | N/A | N/A | 2021-08-04 | 66162.4 | 66162.4 | 300 | 2021-08-04 08:30 | Local (Non-MPO) | 0020067881 [PE] | TR | #N/A
1902767 | B-42802 | Seymour | Johnson | Not Applicable | N/A | Johnson County | Bridge 98 on CR 700E over Fisher Ditch - 0.01 mi N or Urmeyville Road | N/A | N/A | 2024-10-09 | 2021-05-04 | 172600 | 172600 | 392 | 2021-05-04 12:45 | Local (Non-MPO) | 0020063887 [PE] | TR | #N/A
1802823 | N/A | Vincennes | Dubois | Not Applicable | N/A | Dubois County | CR 600W at NS AAR# 724930J in Dubois County | N/A | N/A | N/A | 2019-05-08 | 333893.7 | 370993 | 1119 | 2021-07-08 16:42 | Local (Non-MPO) | 0020035049 [RR] | TR | #N/A

## PED's next 9 Months
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Project End Date | Federal | Expenditure | FMIS Balance | PO Unliquidated | Open POs | Fund Sponsor | PCO Des Status | PED Expiration Days | PCO Task ID
1500229 | PLC-38260 | Crawfordsville | Clay | Not Applicable | N/A | Clay County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 316612.16 | 311998.24 | 4613.92 | 4613.92 | 0020002552 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1500231 | PLC-38261 | Crawfordsville | Clinton | Not Applicable | N/A | Clinton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 248006.4 | 224352.56 | 23653.84 | 23653.84 | 0020051600 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1500252 | PLC-38268 | Crawfordsville | Tippecanoe | Not Applicable | N/A | Tippecanoe County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-12-31 | 775305.68 | 723830.17 | 51475.51 | 51475.51 | 0020004688 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1801364 | N/A | Crawfordsville | Vigo | Terre Haute | N/A | MPO - Terre Haute | Terre Haute MPO Unified Work Program UPWP, PL & HSIP for FY 2019-2020 | 2022-06-30 | 557416 | 496257.8 | 61158.2 | 61158.2 | 0020044242 [PL] | Local (MPO) | TR | 30 | 105959
1592864 | N/A | Fort Wayne | Adams | Not Applicable | N/A | Adams County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 269329.6 | 253988.2 | 15341.4 | 15341.4 | 0018815678 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1173219 | B-35619 | Fort Wayne | Allen | Fort Wayne | Fort Wayne (1165) | Indiana State Agencies | IPFW Pedestrian Bridge over Coliseum Blvd | 2023-02-28 | 4121833.79 | 4072903.01 | 48930.78 | 50366.59 | 0020058242 [CN] | Local (MPO) | TR | 273 | #N/A
1592872 | N/A | Fort Wayne | Allen | Not Applicable | N/A | Allen County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 697827.02 | 696976.88 | 850.14 | 6 | 0018815672 [PE] | Local (Non-MPO) | TR | 61 | #N/A
1592887 | N/A | Fort Wayne | Elkhart | Not Applicable | N/A | Elkhart County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 405110.82 | 404466.34 | 644.48 | 644.48 | 0020001180 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1592891 | N/A | Fort Wayne | Kosciusko | Not Applicable | N/A | Kosciusko County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-03-31 | 220399.65 | 214986.37 | 5413.28 | 5413.28 | 0018812316 [PE] | Local (Non-MPO) | TR | -61 | #N/A
1801325 | N/A | Greenfield | Delaware | Muncie | N/A | MPO - Muncie | Delaware-Muncie MPO Unified Work Program UPWP, PL & STBG for FY 2019-2020 | 2022-06-30 | 561774 | 531129.06 | 30644.94 | 30644.94 | 0020023023 [PL] | Local (MPO) | TR | 30 | 105125
1500279 | N/A | Greenfield | Delaware | Not Applicable | N/A | Delaware County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 432891.42 | 409120.78 | 23770.64 | 23770.64 | 0020004711 [PE] | Local (Non-MPO) | TR | 245 | 105885
1500281 | N/A | Greenfield | Hamilton | Not Applicable | N/A | Hamilton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-03-01 | 473885.78 | 470738.94 | 3146.84 | 3146.84 | 0018800503 [PE] | Local (Non-MPO) | TR | -91 | #N/A
1500282 | N/A | Greenfield | Hancock | Not Applicable | N/A | Hancock County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 232639 | 217388.25 | 15250.75 | 15250.75 | 0018816854 [PE] | Local (Non-MPO) | TR | 30 | #N/A
1500284 | N/A | Greenfield | Howard | Not Applicable | N/A | Howard County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 320104.99 | 313674.57 | 6430.42 | 297.82 | 0020004712 [PE] | Local (Non-MPO) | TR | 273 | #N/A
1801321 | N/A | Greenfield | Howard | Kokomo | N/A | MPO - Kokomo | Kokomo MPO Statement of Work(SOW), PL & STBG for 2019-2020 | 2022-07-30 | 437199 | 417728.44 | 19470.56 | 19470.56 | 0020023021 [PL] | Local (MPO) | TR | 60 | 105236
1801218 | N/A | Greenfield | Madison | Anderson | N/A | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2022-06-30 | 1289730 | 1227341.57 | 62388.43 | 3299.45 | 0020022816 [PL] | Local (MPO) | TR | 30 | 105237
1500286 | N/A | Greenfield | Madison | Not Applicable | N/A | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 471974.47 | 467489.87 | 4484.6 | 4484.6 | 0020046599 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1500287 | N/A | Greenfield | Marion | Indianapolis | N/A | Marion County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 1672548.9 | 1609083.82 | 88783.36 | 88783.36 | 0018818297 [PE] | Local (MPO) | TR | 61 | #N/A
1592159 | N/A | LaPorte | Jasper | Not Applicable | N/A | Jasper County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 213407.2 | 177422.55 | 35984.65 | 35984.65 | 0020002482 [PE] | Local (Non-MPO) | TR | 183 | #N/A
1600452 | N/A | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Greenwood Ave at CSX DOT #232075P in Michigan City | 2023-01-01 | 451828 | 321975.14 | 129852.86 | 129852.86 | 0020013247 [RR] | Local (MPO) | TR | 215 | #N/A
1600449 | N/A | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tilden Street at CSX RR DOT #232080L in Michigan City | 2023-01-01 | 403432 | 367491.62 | 35940.38 | 35940.38 | 0020013249 [RR] | Local (MPO) | TR | 215 | #N/A
1600454 | N/A | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Carroll Ave at CSX DOT #232077D in Michigan City | 2023-01-01 | 443752 | 401608.84 | 42143.16 | 42143.16 | 0020013248 [RR] | Local (MPO) | TR | 215 | #N/A
1600448 | N/A | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tryon Road at CSX DOT #232070F and Royal Rd DOT# 232071M in Michigan City | 2023-01-01 | 1289231 | 1245362.75 | 43868.25 | 43868.25 | 0020012795 [RR] | Local (MPO) | TR | 215 | #N/A
1600451 | N/A | LaPorte | LaPorte | Michigan City | N/A | Indiana Department of Transportation | Roeske Ave at CSX DOT #232074H in Michigan City | 2023-01-01 | 496418 | 403563.44 | 92854.56 | 92854.56 | 0020013246 [RR] | Local (MPO) | TR | 215 | #N/A
1601151 | N/A | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Crown Point (1112) | Crown Point | Purchase E-85 Fuel | 2022-12-30 | 136100.92 | 77133.61 | 58967.31 | 18866.39 | 0020062124 [PE] | Local (MPO) | TR | 213 | #N/A
0900064 | R-33678 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Indianapolis Blvd Complete St Project: from 152nd St to Columbus Dr. (US 12) | 2022-10-31 | 635979.55 | 559144.35 | 76835.2 | 76835.2 | 0018818554 [PE] | Local (MPO) | TR | 153 | #N/A
0810541 | R-35690 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Hobart (1220) | Hobart | Downtown Hobart along Third Street from Main Street to Center Street | 2023-02-08 | 4548999.27 | 4431826.24 | 117173.03 | 130613.83 | 0017819613 [CE]; 0020066600 [CN] | Local (MPO) | TR | 253 | #N/A
1592160 | N/A | LaPorte | Lake | Not Applicable | N/A | Lake County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 697199.13 | 672318 | 24881.13 | 24881.13 | 0020002481 [PE] | Local (Non-MPO) | TR | 92 | #N/A
9981680 | N/A | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | N/A | Lake County | Veterans Memorial Trail (Lake County Conrail Rails to Trails) | 2023-01-28 | 1899392 | 701300.51 | 1711994.5 | 823091.49 | 0016817335 [ROW] | Local (MPO) | TR | 242 | 105858
1592161 | N/A | LaPorte | Marshall | Not Applicable | N/A | Marshall County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 247765.26 | 237695.66 | 10069.6 | 10069.6 | 0020047168 [PE] | Local (Non-MPO) | TR | 245 | 105886
1601122 | N/A | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Chesterton (1083) | Indiana Department of Transportation | 15th Street at CSX Railroad DOT # 232115K in Chesterton | 2023-01-01 | 363000 | 342577.45 | 20422.55 | 18062.1 | 0020011555 [RR] | Local (MPO) | TR | 215 | #N/A
1592163 | N/A | LaPorte | Porter | Not Applicable | N/A | Porter County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 299629.54 | 283168.3 | 16461.24 | 16461.24 | 0018816842 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1592164 | N/A | LaPorte | Pulaski | Not Applicable | N/A | Pulaski County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 171488.2 | 115808.03 | 55680.17 | 55680.17 | 0020002545 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1592155 | N/A | LaPorte | Starke | Not Applicable | N/A | Starke County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-12-31 | 147281.44 | 142222.2 | 5059.24 | 4588.85 | 0020004708 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1801362 | N/A | LaPorte | Various | South Bend (MI) | N/A | MPO - South Bend / Elkhart | MACOG MPO Unified Work Program CMAQ, STBG & HSIP for FY 2019-2020 | 2022-06-30 | 2239178 | 2210865.83 | 28312.17 | 28312.15 | 0020022274 [PL] | Local (MPO) | TR | 30 | 105971
1801359 | N/A | LaPorte | Various | Chicago - Northwestern Indiana (IL) | N/A | MPO - Northwest | NIRPC MPO Unified Work Program UPWP, PL, STBG and CMAQ for FY 2019-2020 | 2022-06-30 | 3246451 | 2609456.78 | 636994.22 | 636992.65 | 0020022992 [PL] | Local (MPO) | TR | 30 | 105123
1592166 | N/A | LaPorte | White | Not Applicable | N/A | White County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 402666.4 | 384444.8 | 18221.6 | 2649.6 | 0020005643 [PE] | Local (Non-MPO) | TR | 245 | 105887
1500192 | PLC-38169 | Seymour | Bartholomew | Not Applicable | N/A | Bartholomew County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 428274.52 | 418068.62 | 10205.9 | 10205.9 | 0018816864 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1500200 | PLC-38170 | Seymour | Brown | Not Applicable | N/A | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-09-30 | 179413.02 | 155777.88 | 23635.14 | 10280.23 | 0020024658 [PE] | Local (Non-MPO) | TR | -243 | #N/A
1500205 | PLC-38175 | Seymour | Franklin | Not Applicable | N/A | Franklin County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 225825.43 | 208381.16 | 17444.27 | 17444.27 | 0020004705 [PE] | Local (Non-MPO) | TR | 245 | 105888
1703018 | B-40891 | Seymour | Jackson | Not Applicable | N/A | Jackson County | Bridge #197-CR 100S over McHargue Ditch, .01 mile East of CR 500W | 2022-06-30 | 200501.6 | 54549.43 | 145952.17 | 145952.17 | 0020023689 [PE] | Local (Non-MPO) | TR | 30 | #N/A
1500208 | PLC-38178 | Seymour | Jefferson | Not Applicable | N/A | Jefferson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 165719.9 | 155151.84 | 10568.06 | 10568.06 | 0020007472 [PE] | Local (Non-MPO) | TR | 273 | #N/A
1500209 | PLC-38179 | Seymour | Johnson | Not Applicable | N/A | Johnson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 285488 | 247269.75 | 38218.25 | 38218.25 | 0018817373 [PE] | Local (Non-MPO) | TR | 61 | #N/A
1801245 | N/A | Seymour | Monroe | Bloomington | N/A | MPO - Bloomington | Bloomington MPO UPWP for FY 2019-2020 | 2022-06-30 | 545584 | 451719.44 | 93864.56 | 61075.13 | 0020021893 [PL] | Local (MPO) | TR | 30 | 105124
1802868 | R-41990 | Seymour | Morgan | Not Applicable | Martinsville (1301) | Martinsville | Along Pike St. beginning at Lincoln St. then 7 blocks to the east to the interse | 2022-12-30 | 123840 | 87853.79 | 35986.21 | 35986.21 | 0020036867 [PE] | Local (Non-MPO) | TR | 213 | #N/A
1802869 | R-41990 | Seymour | Morgan | Not Applicable | Martinsville (1301) | Martinsville | Along Harrison St. beginning at Lincoln St then 6 blocks to the east to the inte | 2022-12-30 | 104480 | 77890.9 | 26589.1 | 26589.1 | 0020035745 [PE] | Local (Non-MPO) | TR | 213 | #N/A
1500213 | PLC-38183 | Seymour | Ripley | Not Applicable | N/A | Ripley County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 214627 | 209482.19 | 5144.81 | 2534.41 | 0020047991 [PE] | Local (Non-MPO) | TR | 245 | 105889
1500215 | PLC-38185 | Seymour | Switzerland | Not Applicable | N/A | Switzerland County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 88899.07 | 87737.47 | 1161.6 | 1161.6 | 0020038641 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1592992 | N/A | Vincennes | Lawrence | Not Applicable | N/A | Lawrence County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 261080.8 | 253398.04 | 7682.76 | 7682.76 | 0018816862 [PE] | Local (Non-MPO) | TR | 30 | #N/A
1592994 | N/A | Vincennes | Orange | Not Applicable | N/A | Orange County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 346677.6 | 338613.82 | 8063.78 | 8063.78 | 0018816852 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1802900 | R-42008 | Vincennes | Pike | Not Applicable | N/A | Pike County | CR 300N from SR 56/61 to Indiana Southern Railroad | 2022-12-12 | 481440 | 203980.1 | 277459.9 | 277459.9 | 0020028791 [PE] | Local (Non-MPO) | TR | 195 | #N/A
1802899 | R-42008 | Vincennes | Pike | Not Applicable | N/A | Pike County | Pike County Bridge 30 over Prides Creek along CR 300 N | 2022-12-12 | 60640 | 29904.8 | 30735.2 | 30735.2 | 0020028797 [PE] | Local (Non-MPO) | TR | 195 | #N/A
1593001 | N/A | Vincennes | Posey | Not Applicable | N/A | Posey County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 381166.29 | 376019.88 | 5146.41 | 5146.41 | 0018816861 [PE] | Local (Non-MPO) | TR | -31 | #N/A
1593021 | N/A | Vincennes | Vanderburgh | Not Applicable | N/A | Vanderburgh County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 339320.64 | 330983.24 | 8337.4 | 8337.4 | 0020004699 [PE] | Local (Non-MPO) | TR | 245 | 105884

## Data
Des # | Task Id | Task Owner
0200120 | 103910 | Summers, Terry
0200120 | 103908 | Summers, Terry
0200120 | 103911 | Summers, Terry
0200120 | 103909 | Summers, Terry
0500067 | 102145 | Davis, Whitney
0500307 | 105837 | Carleton, Greg
0500636 | 105708 | Mischler, Brandi
0500636 | 105938 | Mischler, Brandi
0600731 | 105893 | Shi, Runfa
0600731 | 105857 | Clark, Steve
0600731 | 105814 | Clark, Steve
0014380 | 105969 | Williamson, Brad
0014380 | 105815 | Williamson, Brad
0710765 | 105882 | Kruger, Jonathon
0710794 | 105881 | Kruger, Jonathon
0800156 | 105784 | Marsischky, Cheri
0800251 | 105848 | Clark, Steve
0800729 | 105812
0901798 | 105913 | Worsham, Susan
0902215 | 105816 | Walker, Matthew
1005579 | 105942 | Bullock, Matthew
1006274 | 105850 | Brockway, Sue
1172245 | 103480 | Travis, Steven
1173122 | 105905
1173573 | 105904
1173573 | 105835
1296321 | 105822 | Tucker, Miguel
1296519 | 105880 | Blake, Mark
1296909 | 104592 | Riggs, Nathan
1296909 | 104593 | Riggs, Nathan
1296909 | 104579 | Riggs, Nathan
1297613 | 105167 | Davis, Whitney
1297755 | 103923 | Fischvogt, Brandi
1297755 | 105903
1298346 | 105846 | Brockway, Sue
1298378 | 98020 | Wilson, Caleb
1298581 | 105892 | Abbott, Kathleen
1298581 | 105895
1298581 | 105896 | Abbott, Kathleen
1383157 | 105964 | Beck, Jennifer
1383176 | 105965 | Beck, Jennifer
1383180 | 105967 | Beck, Jennifer
1383245 | 105908
1383558 | 105813 | Bales, Donald
1383558 | 105919 | Bales, Donald
1400106 | 105897 | Abbott, Kathleen
1400109 | 105910 | Summers, Terry
1400149 | 105911 | Summers, Terry
1400243 | 105952
1400297 | 105821
1401183 | 103898 | Davis, Whitney
1401684 | 105830 | Schneider, Chase
1401684 | 105831
1401684 | 105829 | Schneider, Chase
1401684 | 105828 | Clark, Steve
1401703 | 105973 | Beck, Jennifer
1401706 | 105974 | Beck, Jennifer
1401709 | 105970 | Beck, Jennifer
1401867 | 105818 | Summers, Terry
1401867 | 105817 | Clark, Steve
1401867 | 105819 | Summers, Terry
1500014 | 105898 | Abbott, Kathleen
1500014 | 105820
1500015 | 105899 | Abbott, Kathleen
1500031 | 105945 | Goff, Terry
1500068 | 103929 | Walker, Matthew
1500172 | 105963
1500205 | 105888 | Fox, Brenda
1500213 | 105889 | Fox, Brenda
1500279 | 105885 | Fox, Brenda
1500303 | 102226 | Wilson, Caleb
1500309 | 105961 | Williamson, Brad
1500523 | 103934 | Walker, Matthew
1500777 | 105788
1500791 | 105787
1592161 | 105886 | Fox, Brenda
1592166 | 105887 | Fox, Brenda
1592274 | 105843
1592463 | 105878 | Douthitt, Aimee
1592840 | 105926 | Heck, Sara
1592840 | 105927 | Heck, Sara
1592886 | 105883 | Fox, Brenda
1592952 | 99236 | Wilson, Caleb
1593021 | 105884 | Fox, Brenda
1593058 | 78508 | Goff, Terry
1600226 | 105936 | James, Karen
1600226 | 105477 | James, Karen
1600308 | 105854 | Metcalf, Karlei
1600412 | 105935 | Bales, Donald
1600501 | 105827 | Bales, Donald
1600501 | 105921 | Bales, Donald
1600505 | 105681 | Carter, Nicole
1600505 | 105682 | Carter, Nicole
1600505 | 105680 | Carter, Nicole
1600655 | 105906
1600655 | 105907
1600730 | 105948 | Marsischky, Cheri
1600819 | 105962 | Beck, Jennifer
1600878 | 105902
1600878 | 105851 | Carter, Nicole
1600912 | 105930 | Riggs, Nathan
1601052 | 105954 | Davis, Alan
1601102 | 105920 | Bales, Donald
1601774 | 105865
1601953 | 105937 | Riggs, Nathan
1601954 | 105934 | Riggs, Nathan
1601971 | 103939 | Carter, Nicole
1601984 | 105929 | Bales, Donald
1601991 | 105856 | Bales, Donald
1602234 | 105900
1602236 | 105901
1700104 | 105966
1700298 | 105876 | Przybylinski, Ashley
1700403 | 105836 | Clark, Steve
1700404 | 105849 | Clark, Steve
1700587 | 98954 | Farmer, David
1700822 | 105923 | Williams, Christine
1700832 | 105833 | Arnold, Troy
1700843 | 105864
1700896 | 105960 | Riggs, Nathan
1700934 | 95643 | Beck, Jennifer
1701055 | 105953
1701346 | 105839 | Tucker, Miguel
1701392 | 105918
1701394 | 105916
1701402 | 105928 | Mayo, Toni
1701406 | 105915
1702046 | 105863
1702107 | 105823 | Clark, Steve
1702107 | 105826
1702107 | 105825 | Williamson, Brad
1702107 | 105824 | Williamson, Brad
1702110 | 105931 | Paauwe, Jonathan
1702133 | 105922
1702133 | 93763 | Wilson, Caleb
1702877 | 105944 | Phillips, Mary
1800310 | 105949 | Jorns, Mary Ann
1800377 | 105873 | Douthitt, Aimee
1800481 | 105951 | Phillips, Mary
1800953 | 105943
1801218 | 105237 | Nsonwu, Emmanuel
1801218 | 105975 | Nsonwu, Emmanuel
1801245 | 105124 | Nsonwu, Emmanuel
1801261 | 105847 | Holder, Jason
1801268 | 104241 | Nsonwu, Emmanuel
1801291 | 104244 | Nsonwu, Emmanuel
1801321 | 105236 | Nsonwu, Emmanuel
1801323 | 104307 | Nsonwu, Emmanuel
1801325 | 105125 | Nsonwu, Emmanuel
1801359 | 105123 | Nsonwu, Emmanuel
1801362 | 105971
1801364 | 105959 | Davis, Whitney
1801435 | 105972 | Beck, Jennifer
1801601 | 105855
1802795 | 105958
1802977 | 105867 | Walker, Matthew
1802977 | 105866 | Walker, Matthew
1900004 | 105783 | Royer-Pitcock, Penny
1900382 | 105852
1900383 | 105841
1900497 | 105853 | Clark, Steve
1900532 | 105947 | Phillips, Mary
1900658 | 105838 | Clark, Steve
1900659 | 105840 | Clark, Steve
1900695 | 105832 | Clark, Steve
1900734 | 105925 | Miller, Jessica
1900734 | 105924 | Brockway, Sue
1900792 | 105950 | Jorns, Mary Ann
1900822 | 104280 | Nsonwu, Emmanuel
1901417 | 105860 | Bennett, Jennifer
1901471 | 105868 | Kruger, Jonathon
1901472 | 105879 | Kruger, Jonathon
1901488 | 105917
1901490 | 105957
1901490 | 105909
1901490 | 105956
1901521 | 105877 | Douthitt, Aimee
1901532 | 105834 | Douthitt, Aimee
1901744 | 104485 | Davis, Whitney
1901884 | 105912 | Worsham, Susan
1901884 | 105914
1902102 | 105955 | Phillips, Mary
1902103 | 98955 | Mischler, Brandi
1902103 | 98956 | Mischler, Brandi
1902172 | 105869 | Douthitt, Aimee
1902656 | 105946 | Phillips, Mary
2000240 | 105932 | Williamson, Brad
2000240 | 105933 | Clark, Steve
2000996 | 105875 | Cleek, Nicole
2000996 | 105874 | Kruger, Jonathon
2001515 | 105939 | Belch, Stephanie
2001515 | 95532 | Bennett, Jennifer
2001516 | 104487 | Davis, Whitney
2001516 | 105894 | Bennett, Jennifer
2001677 | 104488 | Davis, Whitney
2001701 | 105845
0400935 | 24924 | Summers, Terry
9981680 | 105858 | Blansett, Marcia
9383910 | 105891 | Eimerman, Jessica
9383910 | 105862 | Eimerman, Jessica
9383910 | 105941 | Eimerman, Jessica
9706600 | 105861 | Wilson, Caleb
9706600 | 105890 | Wilson, Caleb
9706600 | 105940 | Wilson, Caleb