## Instructions
Instructions
Scope of services should follow the Work Breakdown Structure Categories
Fees should be broken down by Task with subtasks by classifcation with hours to justify requested fee
Applicable subtasks listed and additional subtasks should be included in the breakdown by classication by hour
The task numbers align closely with prequalfication worktypes and are for reference only. Order should be maintained.
Fee proposals should be submitted in excel format to verify calculations
Tasks should be separate tabs in one excel document.
A fee summary is provided on the WBS tab, suggest hiding the descriptions column, entering Y or Yes in scope items included and filter by Y or Yes to create fee summary

## WBS
Work Breakdown Structure (WBS) |  | Contract Number - Des Number - Route | 12/12/2025 Version |  |  | Proposed Fee Summary
Category | For Reference Only | Task | Recommended Fee Type | Funding Type | Description | Included in Scope of Services (Y/N) | Prime | Subconsultant | Subconsultant | Subconsultant | Subconsultant | Subconsultant | Total
Project Management | 0 | Project Management | Lump Sum | PE | This task should be utilized by the Prime Only, subconsultant project management task should be included in their respective tasks. These hours should not be repeated by the prime in individual tasks. Examples: Progress Reports, Invoice development, QC subconsultant work
Project Intent & System Planning | 1.1 | Abbreviated Engineeer's Report | Lump Sum | PE | See Engineering Assessment Manual
Project Intent & System Planning | 1.2 | Alternative Analysis | Lump Sum | PE | For Historic Bridge AA see bridge section.
Project Intent & System Planning | 1.3 | Engineer's Report | Lump Sum | PE | See Engineering Assessment Manual
Project Intent & System Planning | 1.4 | Interchange Access Request | Lump Sum | PE | See State of Indiana Intersection Access Request Procedure
Project Intent & System Planning | 2.1 | Traffic Data Collection | Lump Sum | PE
Project Intent & System Planning | 2.2 | Traffic Forecasting | Lump Sum | PE
Traffic Capacity and Operations Analysis | 3.1 | Non-Complex Traffic Capacity and Operations Analysis | Lump Sum | PE | Traffic capacity and operations analysis is defined as the assessment of capacity to convey traffic and adequacy of service to users for existing and planned transportation facilities. This work type is defined as, routine traffic capacity and operations analysis of low to moderate complexity. Examples in this class include assessment of rural highways, basic freeway segments, roundabouts and isolated and simple intersections and interchanges. The assessment of capacity to convey traffic and adequacy of service to users for existing and planned roundabouts principally involves the use capacity analysis software, such as ARCADY, SIDRA, RODEL, HCM 2010 or equivalent.
Traffic Capacity and Operations Analysis | 3.2 | Complex Traffic Capacity and Operations Analysis | Lump Sum | PE | Traffic capacity and operations analysis is defined as the assessment of capacity to convey traffic and adequacy of service to users for existing and planned transportation facilities. This work type principally involves application of analytical procedures for freeways, two- and multilane highways, intersections, pedestrian elements, etc. outlined in the Highway Capacity Manual (HCM); in select cases, supplemented by other conventional means of gauging quality of traffic operation (e.g., micro simulation and related modeling techniques). Complex traffic capacity and operations analysis refers to multiple related intersections in a series or grid, non-routine complex interchanges, or a series of related interchanges.
Traffic Safety Analysis | 4 | Traffic Safety Analysis | Lump Sum | PE | Traffic Safety Analysis is the assessment of conditions with respect to traffic safety. This form of highway and street operations analysis involves collection and reduction of crash data; assessment of crash patterns, frequency, and rates; recognition of cause and effect; prediction of crash risk; and selection of effective countermeasures. The engineering task systematically applies analytical procedures at regional and site-specific levels.
Environmental Services | 5.1 | Environmental Documentation - EA/ EIS | Lump Sum | PE | An Environmental Assessment (EA) is a decision document. An EA is prepared to enable the agency to make a decision as to whether the project requires preparation of an EIS or has no significant impact to the human environment. Environmental Impact Statements (EIS) are prepared for major transportation actions that result in significant adverse impacts to the human environment. Coordination with resource agencies and a number of technical environmental studies is expected to be necessary, resulting in the identification of significant adverse impacts, suitable mitigation measures and the preparation of an EIS.
Environmental Services | 5.2 | Environmental Documentation - CE | Lump Sum | PE | Include assumed level, Categorical Exclusions are actions which meet the definition contained in 40 CFR 1508.4 and, based on past experience with similar actions, do not involve significant social, economic or environmental impacts.
Environmental Services | 5.3 | Environmental Documentation - Section 4(f) | Lump Sum | PE | Environmental Section 4(f) as defined in 48 U.S.C. 303, 23 U.S.C. 138 and 23 CFR 771.135 documents are prepared for any level of project that affects, or has the potential to affect, a Section 4(f) resource. Section 4(f) documentation may be a Determination of Use of Section 4(f), a Programmatic Section 4(f) Evaluation or an Individual Section 4(f) Evaluation.
Environmental Services | 5.4 | Ecological Surveys | Lump Sum | PE | Includes Wetland Delineation and Waters Report; An ecological survey is an ecological analysis of the following major areas: water quality, aquatic ecosystems, endangered species, wetlands and terrestrial ecosystems. For projects involving instream work, wetlands, or significant amounts of new right of way, literature searches and ecological surveys are performed to inventory the resources in the vicinity of the proposed project. The data is analyzed and an ecological survey report is prepared. This report presents the data, interprets it and predicts impacts based on preliminary project design.
Environmental Services | 5.5 | Stream and Wetland Mitigation | Lump Sum | PE | Stream and wetland mitigation involves the location, design, construction, restoration, enhancement, monitoring and maintenance of streams and wetlands required as replacement for resources impacted by construction activity.
Environmental Services | 5.6 | Waterway Permits | Lump Sum | PE | Permits for temporary or permanent impacts resulting from construction activity occurring within a regulated wetland, waterway or floodplain may be required. The U.S. Army Corps of Engineers (USACE) 404 permit, Indiana Department of Environment Management (IDEM) 401 Water Quality Certification and Indiana Department of Natural Resources (IDNR) Construction in a Floodway permit are the three primary permits that may be required for INDOT projects.
Environmental Services | 5.7 | Air Quaility Analysis | Lump Sum | PE | An air quality analysis is performed for highway projects where construction causes an increase in traffic sufficient enough to create an impact on the surrounding air quality. The analysis must quantify these impacts for carbon monoxide only in non-attainment areas.
Environmental Services | 5.8 | Noise Analysis and Abatement Design | Lump Sum | PE | A traffic noise analysis is performed for new highway construction or highway improvement for the following purposes: defining areas of potential noise impacts for each study alternative, evaluating measures to mitigate these impacts, and comparing the various study alternatives on the basis of potential noise impact and associated mitigation costs.
Environmental Services | 5.9 | Archaeological Investigation | Lump Sum | PE | INDOT’s scope of services for archaeological investigations include, but are not limited to the following activities: 1. Phase 1a, 1b and 1c field reconnaissance and preparation of associated reports. 2. Phase II test excavations and preparation of associated reports. 3. Phase III mitigation or data recovery excavations and preparation of associated reports. 4. Preparation of Cemetery Development Plans per IC 14-21-1-26.5 5. Preparation of National Register Nomination applications. 6. Consultation with the State Historic Preservation Officer, agency officials and other Section 106 consulting parties, including sending invitations, preparing early coordination letters and holding consulting parties meetings. 7. Preparation of the Section 106 Recommendation for Area of Potential Effect, Eligibility Determination(s), Effect Finding and Section 4(f) Compliance Requirements for Historic Properties and supporting 800.11(d) or 800.11(e) documentation. 8. Preparation of Memorandum of Agreement documents recording the terms and conditions agreed upon to resolve the adverse effects of an undertaking on historic resources. 9. Preparation of Certificate of Approval as required by IC 14-21-1-18 (a) and (b)
Environmental Services | 5.1 | Historical/Architectural Investigation | Lump Sum | PE | Historical/Architectural Investigations and equivalent INDOT scope of services stages are: 1. Determinations of areas of potential effect. 2. Identification of cultural properties (research and fieldwork) including historic property/district reports. 3. Prepare boundary determinations. 4. Determinations of eligibility. 5. Preliminary Findings of effect. 6. Consult with consulting parties, including sending invitations and holding consulting parties meetings. 7. Consult with the State Historic Preservation Officer and other agency officials. 8. National Register preparation. 9. HABS/HAER documentation. 10. Prepare the INDOT/FHWA Area of Potential Effect, Eligibility Determination(s), and Effect Finding form. 11. Prepare INDOT/FHWA 800.11(d) or 800.11(e) documentation. 12. Prepare INDOT/FHWA Memorandum of Agreement documentation.
Environmental Services | 5.12 | Karst Evaluation | Lump Sum | PE | Karst evaluations are conducted to determine the presence or absence of karst features in the area surrounding transportation projects located in the karst regions of the state. Karst regions are characterized by the presence of limestone or other soluble bedrock material and the formation of sinkholes, sinking streams, springs and caves. Karst topography results in the subterranean movement of water. A karst evaluation includes the review of existing information and research, outreach activity, identification and classification of karst features, and proposed treatment of karst features to provide protection from contamination.
Environmental Services | 5.13 | ESA Screening and Phase 1 ESA | Lump Sum | PE | Environmental Site Assessment (ESA) is the investigative process utilized to determine if a parcel of property has been impacted with hazardous substances and/or petroleum products. The primary purpose of the ESA process is to establish a defense to Comprehensive Environmental Response Compensation and Liability Act (CERCLA) liability. An ESA is required when land acquisition is necessary for highway development or when study of properties suspected of being impacted by hazardous substances and/or petroleum products are adjacent to or near transportation projects. The ESA screening and Phase I ESA are investigations into the current and/or past practices using guidance from ASTM 1528-14 Standard Practice for Limited Environmental Due Diligence: Transaction Screen Process and ASTM 1527-13 Standard Practice for Environmental Site Assessments: Phase I Environmental Site Assessment Process. The completion of these documents enables INDOT to integrate issues resulting from environmental impacts into property acquisition and project planning.
Environmental Services | 5.14 | Phase II ESA | Lump Sum | PE | A Phase II Environmental Site Assessment (ESA) and/or further site investigation/corrective action as defined by the IDEM Remediation Closure Guide may be necessary if INDOT determines that acquisition of a contaminated parcel of land is necessary for highway development, or if the Phase I ESA/Screening Transaction process determines that a property adjacent to or near a transportation project may impact that project. The Phase II ESA will be performed in accordance with ASTM E1903-11 Standard Practice for Environmental Site Assessments: Phase II Environmental Site Assessment Process. Further site investigation and/or corrective action will be developed and implemented in accordance with the IDEM’s Non rule Policy Document, Remediation Closure Guide, or as directed by specific IDEM program guidance.
Environmental Services | 5.15 | Red Flag Investigation | Lump Sum | PE | In general, the purpose of a Red Flag Investigation (RFI) is to:  Provide a general overview of the environmental condition of a project area,  Highlight areas that may need additional environmental work or coordination,  Highlight areas that you might want to avoid or minimize impacts (i.e., Superfund site, wetland mitigation site, or similar); and  Assist in prioritizing projects. There are five (5) sections that are evaluated in an RFI for each project. The sections are:  Infrastructure  Water Resources  Mining and Mineral Exploration  Hazardous Material Concerns  Ecological Information
Environmental Services | 5.16 | Environmental Justice | Lump Sum | PE | An environmental justice analysis is required for any project that may result in a disproportionately high adverse impact on a minority or low-income population in or near the project area. The requirements for analysis depend on the level of document and the type of impacts.
Environmental Services | 5.17 | Public Hearing | Each | PE | Required Meeting
Environmental Services | 5.18 | Public Information Meeting | Each | PE | Optional Meeting
Environmental Services | 5.19 | Public Involvement | Lump Sum or Hourly | PE | Other outreach not included in Public Hearing or Information meetings
Environmental Services | 5.2 | Construction Stormwater General Permit | Lump Sum | PE | The Construction Stormwater General Permit (CSGP) applies to all "construction activity" that results in the disturbances of one (1) acre or more of land area. Areas smaller than one (1) acre are also regulated under the CSGP if the project is part of a "larger common plan of development or sale".
Topographical Survey Data Collection | 6.1 | Topographical Survey | Lump Sum | PE | Topographic survey data collection provides the designers with the necessary ground and property information to complete the design and right-of-way acquisition for any project. The data is collected, processed and delivered in an electronic format for the designer to use to prepare the planimetrics and the design Triangulated Irregular Network (TIN) models. This is used to define the existing ground information so that the designer can compute quantities and right-of-way requirements.The survey Consultant shall be responsible for collecting all of the data necessary for the design topography and the property information necessary to write the deeds for any additional right-of-way needed. They are also responsible for the preparation of the survey field book and the field portion of the Location Control Survey Route Plat.
Topographical Survey Data Collection | 6.1.1 | Lidar Survey | Lump Sum | PE | Utilization of mapping technology with laser pulses to calculate distances and measure ranges
Topographical Survey Data Collection | 6.3 | Location Control Route Survey | Lump Sum | PE | This document gives the location of the centerline and its relationship with the existing United States Property Land System (USPLS) land corners, property corners and subdivision corners of interest for the project. The survey Consultant shall be responsible for collecting all of the data necessary for the design topography and the property information necessary to write the deeds for any additional right-of-way needed.
Topographical Survey Data Collection | 6.4 | Boundary Survey | Lump Sum | PE
Topographical Survey Data Collection | 6.6 | Unmanned Aerial System (UAS) Survey | Lump Sum | PE
Geotechnical Services | 7.1 | Geotechnical Exploratory Field and Laboratory Testing Services (PE) | Unit Price | PE
Geotechnical Services | 7.2 | Geotechnical Engineering (PE) | Lump Sum or Hourly | PE
Road Design and Plan Development | 8.1 | Road Design and Plans |  | PE | Including pavement markings and signing
Road Design and Plan Development | Sub Tasks | Engineering Assessment Report (3R/4R Scope) | Lump Sum | PE
Road Design and Plan Development | Sub Tasks | Engineering Assessment Report (PM Mini-Scope) | Lump Sum | PE
Road Design and Plan Development | Sub Tasks | Initial Site Visit and Field Work | Lump Sum | PE
Road Design and Plan Development | Sub Tasks | Grade Review Meeting | Lump Sum | PE | New or Reconstruction, Rehabilition
Road Design and Plan Development | Sub Tasks | Interchange Geometrics Submission to FHWA | Lump Sum | PE | New or Reconstruction
Road Design and Plan Development | Sub Tasks | Geometrics Road Review for Reduced Conflict Intersection Submissions | Lump Sum | PE | New or Reconstruction
Road Design and Plan Development | Sub Tasks | STG1 Review Submission | Lump Sum | PE | New or Reconstruction, Rehabilition, Partial 3R
Road Design and Plan Development | Sub Tasks | Geotechnical Investigation Request / MSE Wall Initial Feasibility Review Submittal | Lump Sum | PE | New or Reconstruction, Rehabilition
Road Design and Plan Development | Sub Tasks | Preliminary Field Check & Minutes | Lump Sum | PE | New or Reconstruction, Rehabilition, Partial 3R
Road Design and Plan Development | 8.1.1 | Preliminary Right-of-Way Plans Preparation | Lump Sum | PE | New or Reconstruction, Rehabilition, Partial 3R
Road Design and Plan Development | Sub Tasks | STG2 Review Submission | Lump Sum | PE | New or Reconstruction, Rehabilition
Road Design and Plan Development | 8.1.2 | Final Right-of-Way Plans | Lump Sum | PE | New or Reconstruction
Road Design and Plan Development | Sub Tasks | Final Field Check Meeting and Minutes | Lump Sum | PE | New or Reconstruction, Rehabilition
Road Design and Plan Development | Sub Tasks | STG3 Review Submission | Lump Sum | PE | New or Reconstruction, Rehabilition, Partial 3R
Road Design and Plan Development | Sub Tasks | Final Tracings Submission | Lump Sum | PE | New or Reconstruction, Rehabilition, Partial 3R
Road Design and Plan Development | 8.2 | Maintenance of Traffic | Lump Sum | PE
Road Design and Plan Development | 8.2.1 | Maintenance of Traffic for Pedestrian & Sidewalks | Lump Sum | PE
Road Design and Plan Development | 8.3 | Traffic Managmement Plan | Lump Sum | PE
Road Design and Plan Development | 8.4 | Design Exception | Lump Sum | PE | Include number of assumed exceptions required
Road Design and Plan Development | 8.6 | Noise Wall Design | Lump Sum | PE
Road Design and Plan Development | 8.7 | Retaining Wall Design | Lump Sum | PE
Bridge Design and Plan Development | 9.1 | Bridge Design and Plans |  | PE
Bridge Design and Plan Development | Sub Tasks | Bridge Rehabilition Field Check and Report | Lump Sum | PE | STG1
Bridge Design and Plan Development | Sub Tasks | Bridge Preventive Maintenance Field Check and Meeting Minutes | Lump Sum | PE | STG1
Bridge Design and Plan Development | Sub Tasks | Bridge Replacement/New Structure Size and Type | Lump Sum | PE | STG1
Bridge Design and Plan Development | Sub Tasks | Historic Bridge Alternatives Analysis | Lump Sum | PE
Bridge Design and Plan Development | Sub Tasks | Bridge Design and Plans - New/Replacement | Lump Sum | PE | Consider subtask for each STG2, 3, FT submittal
Bridge Design and Plan Development | Sub Tasks | Bridge Design and Plans - Rehabilitation | Lump Sum | PE | Consider subtask for each STG2, 3, FT submittal
Bridge Design and Plan Development | Sub Tasks | Bridge Design and Plans - Preventive Maintenance | Lump Sum | PE | Consider subtask for each STG2, 3, FT submittal
Bridge Design and Plan Development | 9.8 | Scour Analysis | Lump Sum | PE | PM and Bridge Rehabs only
Traffic Design & Plans | 10.1 | Traffic Signal Design | Lump Sum | PE
Traffic Design & Plans | 10.2 | Traffic Signal System Design | Lump Sum | PE
Traffic Design & Plans | 10.3 | Complex Roadway Sign Design | Lump Sum | PE
Traffic Design & Plans | 10.4 | Lighting Design | Lump Sum | PE
Traffic Design & Plans | 10.5 | Intelligent Transportation System (ITS) Design | Lump Sum | PE
Traffic Design & Plans | 10.6 | Intelligent Transportation System (ITS) Integration | Lump Sum | PE
Right of Way Plan Development | 11.1 | Right of Way Engineering | Lump Sum or Per Parcel | PE | including Plats, Descriptions and Transfer Documents. Direct non-salary cost should be included in unit price.
Right of Way Plan Development | 11.1.1 | Right of Way Plans | Lump Sum | PE
Right of Way Plan Development | Sub Tasks | Preliminary Right-of-Way Plans | Lump Sum | PE
Right of Way Plan Development | Sub Tasks | Final Right-of-Way Plans | Lump Sum | PE
Right of Way Plan Development | 11.2 | Right of way Staking | Per Parcel | PE | Direct non-salary expenses should be included in unit price.
Right of Way Acquisition Services Category |  | See Fee Schedule for Real Estate Services https://www.in.gov/indot/projects/real-estate/current-real-estate-fee-schedules/ |  | PE
Right of Way Acquisition Services Category | 12.1 | Project Management for Right of Way Acquisition Services | Per Parcel | PE or RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.2 | Title Research | Per Parcel | PE | also called Abstracting, include title & encumberance updates. Document parcel types such as Temporary or Permanent and its use (i.e. Residential,Commercial..). Direct non-salary expenses should be included in unit price.
Right of Way Acquisition Services Category | 12.3 | Value analysis | Per Parcel | PE or RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.4 | Appraisal | Per Parcel | PE or RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.4.1 | Appraisal Problem Analysis | Per Parcel | PE or RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.5 | Appraisal Review | Per Parcel | PE or RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.6 | Early Assessment of Right of Way | Per Parcel | RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.7 | Closing | Per Parcel | RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.8 | Relocation | Per Parcel | RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.8.1 | Relocation Review | Per Parcel | RW | Include Type, direct non-salary expenses should be included in unit price
Right of Way Acquisition Services Category | 12.9 | Buying | Per Parcel | RW | Include Type, includes negotiation. Direct non-salary expense should be included in unit price.
Construction Inspection | 13.1 | Construction Inspection | Negotiated Labor Rate | CE
Utility Coordination Services | 16.1 | Utility Coordination | Lump Sum | PE
Utility Coordination Services | 16.2 | Utility Relocation Inspection Services | Labor Rate Multiplier | PE
Hydraulic Engineering | 17.2 | Small Structure and Pipe Hydraulic Design | Lump Sum/ Per Small Structure | PE
Hydraulic Engineering | 17.3 | Storm Sewer Hydraulic Design | Lump Sum | PE
Hydraulic Engineering | 17.4 | Bridge Hydraulic Design | Lump Sum | PE
Hydraulic Engineering | 17.5 | Detention Hydraulic Design | Lump Sum | PE
Hydraulic Engineering | 17.6 | Roadside Ditches Hydraulic Design | Lump Sum | PE
Hydraulic Engineering | 17.7 | Post-Construction Stormwater Management (Water Quality Analysis) | Lump Sum | PE | Related to Construction Stormwater General Permitting and BMP https://www.in.gov/indot/engineering/environmental-services/storm-water/
Pavement Analysis-Design Services | 18.1 | Pavement Analysis-Design Services |  | PE
Construction Phase Services | 20.1 | Construction Phase Services | Labor Rate Multiplier | PE | Including post letting utility coordination, Shop Drawing Review, RFI Response, Construction changes, preconstruction conference attendance. Rule of thumb fees, $5k (for projects with Estimated Construction Cost< $1M) to $10k (for projects with Estimated Construction Cost > $1M) for Construction Phase Services. This amount may be negotiated depending on project complexity.
Other | 25.1 | Railroad Coordination | Lump Sum | PE
Other | 25.2 | Landscaping Design | Lump Sum | PE
Other | 25.3 | Subsurface Utility Engineering Services | Lump Sum | PE
Other | 25.4 | Water main design | Lump Sum | PE
Other | 25.5 | Sanitary design | Lump Sum | PE
Other | 25.6 | Architectural design | Lump Sum | PE
Other | 25.7 | Financial Management Plan | Lump Sum | PE
Other | 25.8 | Direct Expenses | Actual Cost | PE | for specialized contracts or cost plus contracts. Direct Expenses for mileage or lodging, etc. should be included in lump sum fees or other at cost fees.
Other | 25.9 | MEP Design | Lump Sum | PE
Other | 25.1 | Civil Site Design | Lump Sum | PE
Other | 25.11 | Interactive Display | Lump Sum | PE
Other | 25.12 | Utility Design for Sanitary Sewer Extension | Lump Sum | PE
Other | 25.13 | Value Engineering | Lump Sum | PE

## Ex. Fee Justification Format
Example Fee Justification Format (Lump Sum)
Des. No./Contract Number: | XXXXXXX/P2403XX
Description: | SR XX HMA Overlay
Task: | Road Design and Plan Development
Direct Labor Costs | Hours by Classification
Sub Tasks | Classification 1 | Classification 2 | Classification 3 | Classification 4 | Classification 5 | Total
Scoping Meeting | 4 |  | 4 |  |  | 8
STG1 Review Submission | [5 empty] | 0
Review Level One Design Criteria | 2 |  | 2 |  |  | 4
Level One Checklist |  |  | 2 |  |  | 2
Design Computations |  | 2 | 2 | 8 |  | 12
Develop Title Sheet | 2 |  |  | 4 |  | 6
Develop Index Sheet |  |  | 1 |  |  | 1
Develop Typical Sections | 1 |  | 2 | 4 |  | 7
Develop Traffic-Maintenance Details | 1 |  | 4 | 4 | 8 | 17
Draft TMP Report | 1 |  | 4 |  |  | 5
Develop Plan and Profile Sheets |  |  | 40 | 80 | 80 | 200
INDOT All Project Commitments Report | 1 |  | 1 |  |  | 2
Quantities Computations | 2 |  | 2 |  | 8 | 12
Preliminary Cost Estimate | 1 |  | 1 |  | 3 | 5
Quality Control/Quality Assurance | 4 |  | 4 | 4 | 4 | 16
Sub Total | [5 empty] | 297
Preliminary Field Check Meeting | 4 |  | 4 |  |  | 8
Incorporate STG 1 Review |  |  | 4 | 8 |  | 12
Develop Traffic Maintenance Details |  |  | 2 | 8 | 8 | 18
Sub Total | [5 empty] | 38
Total Hours | 23 | 2 | 79 | 120 | 111
Hourly Rate | 200 | 180 | 160 | 140 | 120
Sub Total Labor Costs | 4600 | 360 | 12640 | 16800 | 13320
[5 empty] | Total Labor Cost | 47720
Direct Costs | Quantity |  | Quantity | Unit | Unit Cost | Subtotal
Mileage | 4 | Trips x | 20 | per Mile | 0.49 | 39.2
Meals | 0 | Person x | 0 | Person/day | 41 | 0
Lodging | 0 | Person x | 0 | Person/night | 107 | 0
Prints | 5 | Sets x | 20 | Each | 0.05 | 5
[5 empty] | Total Direct Expense Cost | 44.2
[5 empty] | Total before rounding | 47764.2
|  |  |  | Road Design and Plan Development | Task Total: | 47800
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Subtasks should be provided as needed to justify hours for deliverables, see Plan Preparation in Indiana Design Manual
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preference would be for these to be the loaded rates with approved overhead, FCCM and advertised profit. See Rate Proposal Template for how this is calculated.
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See approved Indiana travel policy under audit information on proposal and contracts website.

## Geotechnical Unit Price
INDOT Approved Fee Schedule
Des. No./Contract Number: | XXXXXXX/P25XXXX
Description: | SR XX HMA Overlay
Task: | Geotechnical Exploratory Field and Laboratory Testing Services (PE)
Item | Description | Quantity | Unit | Unit Price | Total
GEOTECHNICAL FIELD
1. | Mobilization and Field Coordination
| a. SPT Rig |  | ea | 321 | 0
| b. CPT |  | ea | 537 | 0
| c. Mileage |  | ea | 4.25 | 0
2. | Truck mounted borings with split spoon sampling
| a. Standard |  | ft | 23 | 0
| b. Night time |  | ft | 27 | 0
3. | Truck mounted borings with drilling fluid
| a. Standard |  | ft | 25 | 0
| b. Night time |  | ft | 29 | 0
4. | Truck mounted core drilling
| a. Standard |  | ft | 46 | 0
| b. Night time |  | ft | 55 | 0
5. | Truck mounted borings
a. Truck mounted borings through bedrock or boulders or concrete pavement
| i. Standard |  | ft | 46 | 0
| ii. Night time |  | ft | 55 | 0
b. Bridge deck coring and restoration
| i. Standard |  | ea | 416 | 0
| ii. Night time |  | ea | 490 | 0
6. | Cone penetrometer testing
a. Set up
| i. Standard |  | 8 | 95 | 0
| ii. Night time |  | ea | 112 | 0
b. Subsurface profiling
| i. Standard |  | ft | 15 | 0
| ii. Night time |  | ft | 17 | 0
c. Profiling with pore pressure measurement
i. Piezometric Saturation
| a. Standard |  | ea | 111 | 0
| b. Night time |  | ea | 130 | 0
ii . Penetration
| a. Standard |  | ft | 17 | 0
| b. Night time |  | ft | 20 | 0
iii. Pore water dissipation test
| a. Standard |  | hr | 226 | 0
| b. Night time |  | hr | 266 | 0
iv. Hydraulic conductivity and consolidation
| a. Standard |  | ea | 89 | 0
| b. Night time |  | ea | 105 | 0
d. Profiling with Shearwave Velocity Measurement
| i. Standard |  | ft | 19 | 0
| ii. Night time |  | ft | 23 | 0
e. Sample
| i. Standard |  | ea | 29 | 0
| ii. Night time |  | ea | 34 | 0
7. | Hand or truck soundings
| a. Standard |  | ft | 15 | 0
| b. Night time |  | ft | 18 | 0
8. | Hand auger drilling
| a. Standard |  | ft | 16 | 0
| b. Night time |  | ft | 18 | 0
9. | Skid mounted borings with split spoon sampling
| a. Standard |  | ft | 36 | 0
| b. Night time |  | ft | 43 | 0
10. | Skid mounted borings using drilling fluid
| a. Standard |  | ft | 38 | 0
| b. Night time |  | ft | 45 | 0
11. | Skid mounted core drilling
| a. Standard |  | ft | 52 | 0
| b. Night time |  | ft | 61 | 0
12. | Skid mounted boring through bedrock or boulders
| a. Standard |  | ft | 54 | 0
| b. Night time |  | ft | 63 | 0
13. | Skid mounted soundings
| a. Standard |  | ft | 21 | 0
| b. Night time |  | ft | 25 | 0
14. | Skid Mounted Cone Penetrometer Testing (CPT)
a. Set up
| i. Standard |  | ea | 137 | 0
| ii. Night time |  | ea | 162 | 0
b. Subsurface profiling
| i. Standard |  | ft | 21 | 0
| ii. Night time |  | ft | 25 | 0
c. Profiling with pore pressure measurement
i. Piezometric Saturation
| a. Standard |  | ea | 131 | 0
| b. Night time |  | ea | 155 | 0
ii. Penetration
| a. Standard |  | ft | 25 | 0
| b. Night time |  | ft | 29 | 0
iii. Pore Water Dissipation Test
| a. Standard |  | hr | 261 | 0
| b. Night time |  | hr | 308 | 0
iv. Hydraulic Conductivity and Consolidation
| a. Standard |  | ea | 101 | 0
| b. Night time |  | ea | 119 | 0
d. Profiling with Shearwave Velocity Measurement
| i. Standard |  | ft | 30 | 0
| ii. Night time |  | ft | 35 | 0
e. Sample
| i. Standard |  | ea | 38 | 0
| ii. Night time |  | ea | 45 | 0
15. | Furnishing of a boat |  | Actual Cost |  | 0
16. | Barge set-up expenses
a. Navigable water
| i. Barge set-up |  | ea | 7119 | 0
| ii. Rental of support equipment and/or boat |  | Actual Cost |  | 0
| iii. Drill rig down time |  | hr | 177 | 0
| b. Non-navigable water barge set-up |  | ea | 5933 | 0
17. | Additional disassembly and reassembly
| a. Navigable water |  | ea | 2486 | 0
| b. Non-navigable water |  | ea | 2260 | 0
18. | Barge mounted borings with split spoon sampling |  | ft | 40 | 0
19. | Barge mounted core drilling |  | ft | 54 | 0
20. | Barge mounted boring through bedrock or boulders |  | ft | 54 | 0
21. | Barge mounted soundings |  | ft | 24 | 0
22. | Casing through water |  | ft | 10 | 0
23. | Uncased sounding through water |  | ft | 7 | 0
24. | Set up for borings and machine soundings
| a. Borings and machine soundings less than 20 ft deep |  | ea | 84 | 0
| b. Rock core borings |  | ea | 142 | 0
25. | Additional 2-in. split spoon sampling |  | ea | 25 | 0
26. | 3-in. split spoon samples |  | ea | 27 | 0
27. | 3-in. Shelby tube samples |  | ea | 75 | 0
28. | Bag samples
| a. 25-lb sample |  | ea | 61 | 0
| b. 5-lb sample |  | ea | 40 | 0
29. | Field vane shear test
| a. Standard |  | ea | 137 | 0
| b. Night time |  | ea | 162 | 0
30. | 4½-in. cased hole |  | ft | 15 | 0
31. | Installation of Geotechnical Instruments
a. Inclinometer casing installation
| i. Standard |  | ft | 18 | 0
| ii. Night time |  | ft | 21 | 0
| b. Piezometer installation up to 25 ft below surface |  | ea | 321 | 0
| c. Piezometer installation deeper than 25 ft below surface |  | ea | 356 | 0
| d. Metal protective outer cover for inclinometer and piezometer casings |  | ea | 149 | 0
32. | Railroad expenses |  | Actual Cost
33. | Twenty-four hour water levels
a. Field measurements per borehole
| i. Standard |  | ea | 45 | 0
| ii. Night time |  | ea | 54 | 0
| b. PVC slotted pipe |  | ft | 7 | 0
34. | Special borehole backfilling
a. 0 to 30 ft
i. SPT
| a. Standard |  | ea | 170 | 0
| b. Night time |  | ea | 198 | 0
ii . CPT
| a. Standard |  | ea | 55 | 0
| b. Night time |  | ea | 64 | 0
b. More than 30 ft
i. SPT
| a. Standard |  | ft | 8 | 0
| b. Night time |  | ft | 9 | 0
ii . CPT
| a. Standard |  | ft | 2.25 | 0
| b. Night time |  | ft | 3 | 0
c. Pavement restoration
| i. Standard |  | ea | 73 | 0
| ii. Night time |  | ea | 85 | 0
35. | Equipment Rental |  | Actual Cost |  | 0
36. | Traffic control |  |  |  | 0
| a. Flag crew |  | day | 904 | 0
| b. Equipment Rental and Professional traffic Control Services |  | day |  | 0
| c. Flag crew with equipment |  | day | 1074 | 0
37. | Centerline surveying |  | Actual Cost |  | 0
38. | Percolation Test
| a. Granular Soils (A-1, A-2, A-3) |  | ea | 2260 | 0
| b. Cohesive Soils (A-4, A-5, A-6, A-7) |  | ea | 3390 | 0
GEOTECHNICAL LABORATORY
39. | Sieve analysis for soils |  | ea | 59 | 0
40. | Hydrometer analysis |  | ea | 69 | 0
41. | Sieve analysis for Aggregates
| a. Analysis by Washing (AASHTO T-11) |  | ea | 92 | 0
| b. Analysis by Using (AASHTO T-27) |  | ea | 160 | 0
42. | Liquid limit |  | ea | 46 | 0
43. | Plastic limit & plasticity index |  | ea | 34 | 0
44. | Liquid Limit Ratio |  | ea | 89 | 0
45. | pH test |  | ea | 19 | 0
46. | Loss on Ignition Test
| a. Loss on Ignition Test (Conventional) |  | ea | 29 | 0
| b. Loss on Ignition Test (Sequential) |  | ea | 62 | 0
| c. Organic content based on Colorimeter |  | ea | 29 | 0
47 | Topsoil Tests
| a. Phosphorus tests |  | ea | 26 | 0
| b. Potassium tests |  | ea | 26 | 0
48 | Moisture Content Test
| a. Moisture Content Test ( Conventional) |  | ea | 8 | 0
| b. Moisture Content Test (Microwave) |  | ea | 10 | 0
49 | Expansion Index of Soils |  | ea | 279 | 0
50 | Specific Gravity Test |  | ea | 43 | 0
51 | Unit weight determination |  | ea | 21 | 0
52 | Hydraulic Conductivity Test
| a. Constant Head |  | ea | 279 | 0
| b. Falling Head |  | ea | 339 | 0
53 | Unconfined Compression Test on soils & Rocks
| a. Unconfined Compression Test (Soils) |  | ea | 57 | 0
| b. Remolding of soil samples with chemical admixtures in chemical soil modification/ stabilization (3 samples is equal to 1 unit) |  | ea | 141 | 0
| c. Point Load Strength Index of Rock |  | ea | 62 | 0
54 | Compressive Strength and Elastic Moduli of Intact Rock
| a. Compressive Strength of Intact Rock |  | ea | 136 | 0
| b. Elastic Moduli of Intact Rock |  | ea | 511 | 0
55 | Consolidation Test |  | ea | 565 | 0
56 | Triaxial test
| a. Unconsolidated - Undrained (UU) |  | ea | 424 | 0
| b. Consolidated - Undrained (CU) |  | ea | 622 | 0
| c. Consolidated - Drained (CD) |  | ea | 876 | 0
| d. Pore Pressure measurement with a. or b. and use of back pressure for saturation |  | ea | 294 | 0
57 | Direct Shear Test |  | ea | 650 | 0
58 | Moisture-Density Relationship Test
| a. Standard Proctor |  | ea | 170 | 0
| b. Modified Proctor |  | ea | 186 | 0
59 | Soil Support Testing
| a. Subgrade Resilient Modulus on remolded soils |  | ea | 746 | 0
| b. Resilient modulus on Shelby tube |  | ea | 475 | 0
60 | Collapse Potential Evaluation Test
| a. Cohesive or Expansive Soils |  | ea | 124 | 0
61 | Water Soluble Sulfate Test |  | ea | 124 | 0
62 | Water Soluble Chloride Test |  | ea | 124 | 0
63 | Soil Resistivity Test |  | ea | 170 | 0
64 | Shale Durability Tests
| a. Slake Durability Index Test |  | ea | 158 | 0
| b. Jar Slake Test |  | ea | 17 | 0
CONSTRUCTION INSPECTION AND MONITORING
74 | Pressuremeter Testing services |  | day | 2034 | 0
75 | Mobilization of testing equipment |  | LS | 226 | 0
77 | Integrity testing |  | Actual Cost |  | 0
79 | Dynamic pile analysis |  | ea | 1243 | 0
81 | Dynamic pile load test |  | Actual Cost |  | 0
82 | CAPWAP-C analysis |  | ea | 678 | 0
PAVEMENT INVESTIGATION
88. | Mobilization of coring equipment |  | LS | 254 | 0
89. | Mobilization mileage for coring equipment |  | mi | 2.25 | 0
90. | Pavement core (partial depth) |  | ea | 158 | 0
91. | Pavement core (full depth)
| a. Standard |  | ea | 243 | 0
| b. Night time |  | ea | 288 | 0
92. | Sub-base sample |  | ea | 75 | 0
93. | Cement concrete pavement core density determination |  | ea | 41 | 0
94. | Cement concrete core compressive strength test |  | ea | 40 | 0
95. | Bituminous extraction test |  | ea | 102 | 0
96. | Sieve analysis of extracted aggregate test |  | ea | 69 | 0
97. | Recovery of asphalt from solution by Abson method |  | ea | 427 | 0
98. | Theoretical maximum specific gravity test |  | ea | 90 | 0
99 | Bulk specific gravity test |  | ea | 40 | 0
100. | Air voids calculation |  | ea | 35 | 0
101. | Core report |  | ea | 74 | 0
|  |  |  | Task Total | 0

## Title Research
Example Fee Justification Format (Lump Sum)
Des. No./Contract Number: | XXXXXXX/P2403XX
Description: | SR XX HMA Overlay
Task: | Title Research
Title Research | Quantity | Unit | Unit Price | Total
Permanent RW 50 Year |  | Parcel |  | 0
Permanent RW |  | Parcel |  | 0
Temporary RW |  | Parcel |  | 0
Title Update |  | Parcel |  | 0
Supplemental Title Research |  | Per Hour |  | 0
|  |  | Total | 0
RW Direct Costs | Quantity |  | Quantity | Unit | Unit Cost | Subtotal
Mileage | 0 | Trips x | 20 | per Mile | 0.49 | 0
Meals | 0 | Person x | 0 | Person/day | 41 | 0
Lodging | 0 | Person x | 0 | Person/night | 107 | 0
Prints | 100 | Sets x | 1 | Each | 0.05 | 5
[5 empty] | Total Direct Expense Cost | 5
[5 empty] | Total before rounding | 5
|  |  |  | Title Research | Task Total: | 100

## SUE Unit Price
Example Fee Justification Format (Lump Sum)
Des. No./Contract Number: | XXXXXXX/P2403XX
Description: | SR XX HMA Overlay
Task: | Subsurface Utility Engineering Unit Price
Utility Designating Services | Quantity | Unit | Unit Price | Total
Utility Designating |  | ft | 1.43
Ground Penetration Radar (GPR) |  | half day | 1300
Ground Penetration Radar (GPR) per day |  | day | 2500
Subsurface Utility Locating (Test Hole) Services
1-10 Holes
Pavement/Shoulder |  | Per Hole <8ft deep | 970
Pavement/Shoulder |  | Per Hole >8ft deep | 1465
Off Pavement |  | Per Hole <8ft deep | 795
Off Pavement |  | Per Hole >8ft deep | 1035
11-25 Holes
Pavement/Shoulder |  | Per Hole <8ft deep | 860
Pavement/Shoulder |  | Per Hole >8ft deep | 1220
Off Pavement |  | Per Hole <8ft deep | 710
Off Pavement |  | Per Hole >8ft deep | 900
26-50 Holes
Pavement/Shoulder |  | Per Hole <8ft deep | 765
Pavement/Shoulder |  | Per Hole >8ft deep | 1020
Off Pavement |  | Per Hole <8ft deep | 635
Off Pavement |  | Per Hole >8ft deep | 780
>50 Holes
Pavement/Shoulder |  | Per Hole <8ft deep | 680
Pavement/Shoulder |  | Per Hole >8ft deep | 850
Off Pavement |  | Per Hole <8ft deep | 565
Off Pavement |  | Per Hole >8ft deep | 680
Vacuum excavation truck
< 60 miles round trip |  | per Task Order | No Charge
60-119 miles round trip |  | per Task Order | 785
>=120 miles round trip |  | per Task Order | 1045
Designation/GPR vehicle and/or Survey Vehicle (includes equipment and crew travel time)
< 60 miles round trip |  | Round Trip | No Charge
60-119 miles round trip |  | Round Trip | 700
>=120 miles round trip |  | Round Trip | 940
Maintenance of Traffic (includes equipment and crew time |  | day | 265
|  |  | Total | 0
Direct Costs | Quantity |  | Quantity | Unit | Unit Cost | Subtotal
Mileage | 4 | Trips x | 20 | per Mile | 0.49 | 39.2
Meals | 0 | Person x | 0 | Person/day | 41 | 0
Lodging | 0 | Person x | 0 | Person/night | 107 | 0
Prints | 5 | Sets x | 20 | Each | 0.05 | 5
[5 empty] | Total Direct Expense Cost | 44.2
[5 empty] | Total before rounding | 44.2
|  |  |  | Subsurface Utility Engineering Unit Price | Task Total: | 100

## SUE Hourly
Subsurface Utility Engineering Hourly
Des. No./Contract Number: | XXXXXXX/P2403XX
Description: | SR XX HMA Overlay
Task: | Subsurface Utility Engineering Hourly
Direct Labor Costs | Hours by Classification
Sub Tasks | Classification 1 | Classification 2 | Classification 3 | Classification 4 | Classification 5 | Total
Sub Total
Total Hours | 0 | 0 | 0 | 0 | 0
Hourly Rate | 200 | 180 | 160 | 140 | 120
Sub Total Labor Costs | 0 | 0 | 0 | 0 | 0
[5 empty] | Total Labor Cost | 0
Direct Costs | Quantity |  | Quantity | Unit | Unit Cost | Subtotal
Mileage | 4 | Trips x | 20 | per Mile | 0.49 | 39.2
Meals | 0 | Person x | 0 | Person/day | 41 | 0
Lodging | 0 | Person x | 0 | Person/night | 107 | 0
Prints | 5 | Sets x | 20 | Each | 0.05 | 5
Permits |  |  |  | Each |  | 0
[5 empty] | Total Direct Expense Cost | 44.2
[5 empty] | Total before rounding | 44.2
|  |  |  | Subsurface Utility Engineering Hourly | Task Total: | 100