Indiana Department of Transportation LEVEL 1 Project Constructability Review 2 Stage 2 Plan Review Submission Project Manager/Construction Manager/Maintenance Manager

Primary DES No. 	 Contract No.

Route 	 District

Work Type	 RFC Date

Project Location

Project Description

County/City/Town 	 Designer

Project Manager

Reviewed by 	Title

Date

| Evaluation Criteria | Y | N | N/A | Note | Flag |
| --- | --- | --- | --- | --- | --- |
| A. Plans - Road |  |  |  |  |  |
| * | 1. Do roadway plans detail positive drainage for each phase of construction? |  |  |  |  |  |
| * | 2. Do roadway plans clearly identify adequacy of pipe and structure location? |  |  |  |  |  |
| * | 3. Are phases of work considered in calculating earthwork balances and appropriate pay items? |  |  |  |  |  |
| * | 4. Is the bridge cone fill quantity shown in the road earthwork balance? |  |  |  |  |  |
| * | 5. Is all earthwork activity reflected? Rock? Peat? |  |  |  |  |  |
| * | 6. Is an earthwork summary in the plans? |  |  |  |  |  |
| * | 7. Are cut/fills accurately shown where match lines are necessary? |  |  |  |  |  |
| * | 8. Are clearing and grubbing limits identified? |  |  |  |  |  |
| * | 9. How is shrink/swell factor applied to earthwork tabulation? |  |  |  |  |  |
| * | 10. Are shrink/swell factors reasonable? |  |  |  |  |  |
|  | 11. Is the quantity of borrow shown on the plans? |  |  |  |  |  |
| * | 12. Is earthwork phasing compatible with construction requirements? |  |  |  |  |  |
| * | 13. Are paving limits shown? |  |  |  |  |  |
| * | 14. Is milling required? |  |  |  |  |  |
| * | 15. Can existing roadway materials be salvaged for other use? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 16. Is blasting allowed? |  |  |  |  |  |
| * | 17. Will excavated rock fit into available fills? |  |  |  |  |  |
| * | 18. Is there rock in drainage trench? Will blasting be required or allowed? |  |  |  |  |  |
| * | 19. How long of period can highway be closed for blasting/clearing? |  |  |  |  |  |
| * | 20. Any presence of ground water or active streams? |  |  |  |  |  |
| * | 21. Is sheeting or shoring necessary to protect roadway? If so, an item will be required. |  |  |  |  |  |
| * | 22. Are buildings to be demolished? An asbestos and lead evaluation will be made. |  |  |  |  |  |
| * | 23. Is illumination (existing) to be maintained during construction? |  |  |  |  |  |
| * | 24. Do driveway/turnout grades meet allowable standards? |  |  |  |  |  |
| * | 25. Consider proposed terrain when locating sign foundations. |  |  |  |  |  |
| * | 26. Are ADA requirements clear and constructible? |  |  |  |  |  |
| * | 27. Is pavement design submitted? Clear and constructable? |  |  |  |  |  |
| B. Plans - Bridge |  |  |  |  |  |
| * | 1. Have foundation locations been checked for ROW infringements? |  |  |  |  |  |
| * | 2. Access to structure site? |  |  |  |  |  |
| * | 3. Is there adequate room for pile driving operations? |  |  |  |  |  |
| * | 4. Consider working areas needs around structures. |  |  |  |  |  |
| * | 5. Are soil conditions compatible for steel shell piling? |  |  |  |  |  |
| * | 6. Will caisson drilling require special measures? |  |  |  |  |  |
| * | 7. Is dewatering required? |  |  |  |  |  |
| * | 8. Has substructure been examined for scour? |  |  |  |  |  |
| * | 9. Is cofferdam required? |  |  |  |  |  |
| * | 10. Ensure that when cofferdam and pumping is an item in the contract, wet excavation is also an item. Is underwater (tremie) concrete required? |  |  |  |  |  |
| * | 11. Are there conflicts between existing foundations and proposed foundations? |  |  |  |  |  |
| * | 12. Are the proper types of retaining walls specified to meet the site characteristics? (i.e. Are cut walls used in fill or fill walls used in cuts?) |  |  |  |  |  |
| * | 13. Have the proposed drainage features (pipes, structures, outlets) been coordinated with the bridge plans; specifically the foundations? |  |  |  |  |  |
| * | 14. Are there conflicts with the bridge foundations and the utilities (existing and relocated)? |  |  |  |  |  |
| * | 15. Is shoring required to build the structure? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 16. Is there enough room, both horizontal and vertical, to construct typical shoring methods between construction phases? |  |  |  |  |  |
| * | 17. Check for overhead utility conflicts. |  |  |  |  |  |
| * | 18. Is there adequate room to install anchor bolts for bearing assemblies? |  |  |  |  |  |
| * | 19. Are the wingwalls too long to be supported without a pile? |  |  |  |  |  |
| * | 20. Is there enough room for all permanent retaining wall elements to fit within the proposed R/W? |  |  |  |  |  |
| * | 21. Are closure pours required for bridges with phased construction? |  |  |  |  |  |
| * | 22. Do post-tensioned elements provide enough room for the PT Jacking equipment? |  |  |  |  |  |
| * | 23. Can Bridge large or heavy members be transported legally without limitations on existing roads, bridges, or hauling equipment? |  |  |  |  |  |
| * | 24. Check out haul routes through metropolitan areas – restrictions? |  |  |  |  |  |
| * | 25. Is there adequate structure vertical clearance over entire project travelway? |  |  |  |  |  |
| C. Cost Estimate (Pay Items, Quantities) |  |  |  |  |  |
| * | 1. Does the estimate include a pay item for all work included in the plans? Do pay items reflect scope of work? |  |  |  |  |  |
| * | 2. Are pay items accurate? |  |  |  |  |  |
| * | 3. Are cost estimates and unit prices appropriate for type of project? |  |  |  |  |  |
| * | 4. Are quantity estimates developed to appropriate level for this review? |  |  |  |  |  |
| * | 5. Are quantities reliable, verifiable? |  |  |  |  |  |
| * | 6. Were quantity calculations of Road and Bridge Plans checked for overlap as well as missing items? |  |  |  |  |  |
| * | 7. Were all temporary items for maintenance of traffic included? |  |  |  |  |  |
| * | 8. Are appropriate partners involved in the estimate review? |  |  |  |  |  |
| D. Site Investigation |  |  |  |  |  |
| * | 1. Is the additional site survey completed as necessary? |  |  |  |  |  |
| * | 2. Is the geotechnical engineering completed as necessary? |  |  |  |  |  |
| * | 3. Is the site drainage plan, including construction phases, being developed? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 4. Review potential drainage problems through temporary construction. |  |  |  |  |  |
| * | 5. Has offsite drainage been considered (beyond construction limits)? |  |  |  |  |  |
| * | 6. Is drainage properly controlled at the ends of structures? |  |  |  |  |  |
| * | 7. Can existing drainage patterns be maintained during construction? |  |  |  |  |  |
| * | 8. Do the pipe sizes and angles fit the existing drainage structures? |  |  |  |  |  |
| * | 9. Is there sufficient R/W to trench drainage structures? |  |  |  |  |  |
| * | 10. Are special structures required because of pipe size or number of pipes? |  |  |  |  |  |
| * | 11. Are existing structures to remain or be reset in good shape? i.e.: frames, grates, walls. |  |  |  |  |  |
| * | 12. Check for conflicts with existing/proposed drainage. |  |  |  |  |  |
| * | 13. What are the locations of Geotech investigations? When were they taken? |  |  |  |  |  |
| * | 14. Has Geotech taken cores of the existing pavement and shoulder to verify the structure of the existing roadway? Where were cores taken? |  |  |  |  |  |
| * | 15. Does structure depth prohibit trenching? |  |  |  |  |  |
| E. Right of Way |  |  |  |  |  |
| * | 1. Has the required R/W been identified and sufficient for the project and all necessary construction operations? |  |  |  |  |  |
| * | 2. Is the clearing and staking contract being developed as applicable? |  |  |  |  |  |
| * | 3. Sufficient R/W available for all operations? |  |  |  |  |  |
| * | 4. Sufficient R/W for equipment and material storage? |  |  |  |  |  |
| * | 5. Staging needs met? |  |  |  |  |  |
| * | 6. Access requirements? |  |  |  |  |  |
| * | 7. Access to work areas? |  |  |  |  |  |
| * | 8. Is temporary R/W for construction access identified? |  |  |  |  |  |
| * | 9. Is there enough Right-of-Way to construct the slopes as shown? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 10. Is there enough work room for the contractor to construct the slopes? |  |  |  |  |  |
| * | 11. Is the Right-of-Way conducive to utility relocates? |  |  |  |  |  |
| * | 12. Is there sufficient R/W to relocate all utilities? |  |  |  |  |  |
| * | 13. Does R/W account for buried drainage features? |  |  |  |  |  |
| * | 14. Is it straight to allow for power pole runs without a bunch of down guys? |  |  |  |  |  |
| * | 15. Do the structures fit in the R/W? |  |  |  |  |  |
| * | 16. Is there enough work room to build the structures on the R/W? |  |  |  |  |  |
| * | 17. Any R/W active commitment? Or is the commitment already in the plans? |  |  |  |  |  |
| * | 18. Are all encroachments and instruction on handling them clearly communicated? |  |  |  |  |  |
| * | 19. Is there a cemetery within the project limits? If so, has a cemetery plan been developed and clearly communicated? |  |  |  |  |  |
| F. Utilities and Railroad |  |  |  |  |  |
| * | 1. Are utility conflicts identified? |  |  |  |  |  |
| * | 2. Are all known utilities indicated on plans? |  |  |  |  |  |
| * | 3. Any Utility active commitment? Or is it in the plans? |  |  |  |  |  |
| * | 4. Are the utilities and drainage shown on the Cross sections? |  |  |  |  |  |
| * | 5. Can reasonable changes be made to avoid utility conflicts? |  |  |  |  |  |
| * | 6. Are utilities to be maintained during construction? If so, are provisions in place? |  |  |  |  |  |
| * | 7. Are any substations or utility appurtenances within the construction area required to be accessed during construction? If so, have provisions been included in specs? |  |  |  |  |  |
| * | 8. Are relocations extensive enough to request an early order to start for utilities? |  |  |  |  |  |
| * | 9. Will overhead utilities be in conflict with proposed construction and/or the use of construction equipment such as cranes or pile drivers? If so, should they be relocated? |  |  |  |  |  |
| * | 10. Are privately owned services involved? Is there a bid item for these relocations? |  |  |  |  |  |
| * | 11. Will utility work impact contaminated soil? Are provisions to perform this work in the agreement? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 12. Are pole relocations in conflict with proposed sidewalks? |  |  |  |  |  |
| * | 13. Are utility durations taken into account with the overall construction schedule? Is it realistic? |  |  |  |  |  |
| * | 14. Identify utility drainage conflicts on plans. |  |  |  |  |  |
| * | 15. Is underground work sequenced with roadway operation? |  |  |  |  |  |
| * | 16. Are soil conditions conducive for trenching? |  |  |  |  |  |
| * | 17. Do catch basins conflict with underground utilities? |  |  |  |  |  |
| * | 18. Is railroad coordination in progress as required? |  |  |  |  |  |
| * | 19. Rail shop drawing submittals, if known require a long lead time, a note should be placed in contract indicating such. |  |  |  |  |  |
| * | 20. Railroad protection or flagger item included in contract if needed. Has a force account with the Railroad been processed? |  |  |  |  |  |
| * | 21. Are there any RR crossings located in the proposed detour route? |  |  |  |  |  |
| * | 22. If required, has railroad insurance been acquired and coordinated? |  |  |  |  |  |
| G. Environmental |  |  |  |  |  |
| * | 1. Are required environmental permits identified & applications drafted? |  |  |  |  |  |
| * | 2. Any Environmental active commitment instead of permits? |  |  |  |  |  |
| * | 3. Have the mitigation requirements been identified & plans developed? |  |  |  |  |  |
| * | 4. Are the E&SC plans & provisions developed & coordinated with agencies? |  |  |  |  |  |
| * | 5. Are the environmental restriction period impacts identified? |  |  |  |  |  |
| * | 6. If contamination exists on the site, have the proper type and quantity of borings and pump tests been performed? |  |  |  |  |  |
| * | 7. If contaminated soil, are there provisions for handling/treating? |  |  |  |  |  |
| * | 8. If the work is located adjacent to a residential area or occupied building, provisions may be required to minimize the impact of noise producing activities, such as restricted work hours or temporary noise barriers. |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 9. Can the roadway and/or structures handle the load of this piece of equipment, the paving train? |  |  |  |  |  |
| * | 10. If present, are historical structures identified on plans with clear instruction on limitations and handling? |  |  |  |  |  |
| H. Traffic Maintenance & Traffic Management Plans |  |  |  |  |  |
| * | 1. Is detour necessary for averting delays/congestion? |  |  |  |  |  |
| * | 2. Adequate turn lanes provided to avoid traffic backups? |  |  |  |  |  |
| * | 3. Have appropriate MOT plan and phases been developed? |  |  |  |  |  |
| * | 4. Is the TMP being developed and coordinated with appropriate entities? |  |  |  |  |  |
| * | 5. Does the TMP adequately address site conditions and traffic volumes? |  |  |  |  |  |
| * | 6. Does the MOT plan address adequate work area for construction operations? Can work be safely accessed? |  |  |  |  |  |
| * | 7. Are conflicts with other work in area of project being addressed? |  |  |  |  |  |
| * | 8. Will ramps have to be closed? |  |  |  |  |  |
| * | 9. Have detours been checked for illumination? |  |  |  |  |  |
| * | 10. Does detour allow enough area for planned work? |  |  |  |  |  |
| * | 11. Check access for local business/residents. |  |  |  |  |  |
| * | 12. Does signing meet traffic needs in each phase? |  |  |  |  |  |
| * | 13. Are work zones large enough for equipment access? |  |  |  |  |  |
| * | 14. Can emergency vehicles travel through zones without delays? |  |  |  |  |  |
| * | 15. Is there adequate vertical clearance in all phases of the MOT? |  |  |  |  |  |
| * | 16. Is power for temporary/permanent utilities available? |  |  |  |  |  |
| * | 17. Check driveways/sidewalks for conflicts with utilities. |  |  |  |  |  |
| * | 18. Is existing drainage affected by the temporary pavement? |  |  |  |  |  |
| * | 19. Was construction loading on bridge decks considered during each phase? |  |  |  |  |  |
| * | 20. Is work zone safety waiver required? If so, has it been acquired? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 21. Is route a special truck route (permitted wide load, extra heavy duty truck route)? If so, does the MOT accommodate these vehicles? |  |  |  |  |  |
| * | 22. Are temporary markings and safety devices proper and sufficient? |  |  |  |  |  |
| I. Construction Phasing |  |  |  |  |  |
| * | 1. Are proposed construction phases appropriate and constructible? |  |  |  |  |  |
| * | 2. Are constructability issues between phases identified and addressed? |  |  |  |  |  |
| * | 3. Have Unique Special Revisions required by the construction phasing been drafted? |  |  |  |  |  |
| * | 4. Phasing to provide minimum number of stages and reasonable work areas and access? |  |  |  |  |  |
| * | 5. Are there areas with restricted access? |  |  |  |  |  |
| * | 6. Are work zone widths adequate for construction equipment needs? |  |  |  |  |  |
| * | 7. Are travel lanes adequate? Width? Number? Wide Loads? |  |  |  |  |  |
| * | 8. Project phasing considered drainage construction? |  |  |  |  |  |
| * | 9. Does staging cause special conditions (i.e. structural adequacy/stability)? If shoulders are required to carry traffic during stage construction, are they structurally adequate or should reconstruction be required? |  |  |  |  |  |
| * | 10. Proposed adjacent contracts, restrictions, constraints identified and accounted for? |  |  |  |  |  |
| * | 11. Can these details, as shown on the plans, be constructed using standard industry practice, operations, and equipment? |  |  |  |  |  |
| * | 12. Will traffic signal preformed loops work with phasing? |  |  |  |  |  |
| * | 13. Are these grade changes between phases that won’t allow access to adjacent properties? |  |  |  |  |  |
| * | 14. Are temporary roadways and pavements required to complete construction? If so, details are required. |  |  |  |  |  |
| * | 15. Should limits of work be staged to minimize disruption to the public? |  |  |  |  |  |
| * | 16. Will existing barriers have to be relocated? |  |  |  |  |  |
| * | 17. If staged construction, has balance of cuts and fills been done for each stage? Are temporary stockpile locations identified on the plans, if needed? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 18. Does proposed drainage function during construction phases? |  |  |  |  |  |
| * | 19. Is bridge construction phasing consistent with road construction phasing? (horizontal & vertical) |  |  |  |  |  |
| * | 20. Do the utility relocation plans work for all phases of construction? |  |  |  |  |  |
| J. Schedule & Special Considerations |  |  |  |  |  |
| * | 1. Is letting schedule appropriate for desired completion date? |  |  |  |  |  |
| * | 2. Does schedule address other work in area or related contracts in project? |  |  |  |  |  |
| * | 3. Does schedule address environmental restriction periods? |  |  |  |  |  |
| * | 4. Does schedule address local events, holidays, etc.? |  |  |  |  |  |
| * | 5. Does schedule address special material procurement time? |  |  |  |  |  |
| * | 6. Does schedule address removal of hazardous materials as necessary? |  |  |  |  |  |
| * | 7. Does schedule address utility relocation timeline? |  |  |  |  |  |
| * | 8. Does schedule address railroad coordination as necessary? |  |  |  |  |  |
| K. General Considerations? |  |  |  |  |  |
| * | 1. Pertinent provisions and restrictions clearly indicated? |  |  |  |  |  |
| * | 2. Any special (unique/proprietary) materials, methods or technologies required for contract? |  |  |  |  |  |
| * | 3. Special coordination required, RR, Permits, Regulatory? |  |  |  |  |  |
| * | 4. Presence of asbestos, hazardous waste or toxic materials? |  |  |  |  |  |
| * | 5. Safety requirements, fall protection, electric lines, and other utilities, RR requirements? |  |  |  |  |  |
| * | 6. Winter concreting? |  |  |  |  |  |
| * | 7. Soils stabilization? |  |  |  |  |  |
| * | 8. Local conditions? |  |  |  |  |  |
| * | 9. Were adverse effects of weather considered in selecting materials or construction methods? |  |  |  |  |  |
| * | 10. Has use of proprietary items been approved? |  |  |  |  |  |
| * | 11. Are there any special construction methods or conditions that need to be described or considered? |  |  |  |  |  |
| Evaluation Criteria | Y | N | N/A | Note | Flag |
| * | 12. Has the cost implications of special construction methods or conditions been considered in the project? |  |  |  |  |  |
| * | 13. Are there any lead times for materials that need to be considered in the overall schedule of the project. |  |  |  |  |  |
| * | 14. How does the project affect the community? |  |  |  |  |  |
| * | 15. Are there any special events that need to be considered? |  |  |  |  |  |
| * | 16. Are there outside impacts that are pushing the overall job costs up that might be mitigated in some manner? |  |  |  |  |  |
| Note No. | REVIEWER COMMENTS |
| Note No. | REVIEWER COMMENTS |
| (Attach additional sheets as necessary) |
| Note No. | DESIGNER COMMENTS |

(Attach additional sheets as necessary)