## Slide 1
Updated History & Projected Engagement
November 2025
US 31 Corridor Projects in Marshall & Fulton Counties
Notes: 1

## Slide 2
US 31 Corridor projects
in Marshall & Fulton
History
HEARINGS
SR 10 and SR 110 J-Turn Public Meeting/Hearings
2017-2019
2020
2014-2016
FUNDING
SR 10 and SR 110 Safety Funds
PUBLIC FEEDBACK
SR 10 interchange initiated
MAPPING
SR 10 Interchange Geometry Design
FEEDBACK
SR 110 and CR 700 Meeting with
Fulton County & Amish

## Slide 3
US 31 Corridor projects
in Marshall & Fulton
History
INDOT
Abbreviated Corridor Report (CR 700 to SR 10)
INDOT ANNOUNCES PEL
Study includes Marshall-Fulton project area
PEL STUDIES START
Vision/scoping
Public Information Meeting 1 Launch of propelus30.com
RFP
Request for proposals (all)
PEL REPORTS & PUBLIC FEEDBACK
Above Ground Cultural Resource Memo, Purpose and Need, Public Information Meeting 2, Draft Environmental Constraints Report, Draft Universe of Alternatives Screening, Level 1
2023
2024
2022
2021
HEARINGS
Study:
Draft Report for SR 10
PROGRESS
Engineer Report Amendment Memo for SR 10
MEETING
Community Advisory Committee for SR 10
MEETINGS
Community Advisory Committee meetings for US 31 @ SR 110, CR700 and access control, 10 & 110 follow-up CACs, PIM

## Slide 4
US 31 Corridor projects
in Marshall & Fulton
History
PROGRESS
Submit Draft Engineers Report SR 10 for INDOT & FHWA Review
2024
PROGRESS
Existing Transportation Conditions Report
Purpose & Need Report FINAL
Universe of Alternatives (Level 1) Screening Report FINAL
PROGRESS
Revise
Public Involvement Plan
PROGRESS
Draft Purpose and Need Report – INDOT Approved
(Currently in FHWA Review)
PROGRESS
Submit Draft Engineers Report SR 110 & CR 700 for INDOT& FHWA Review
MEETINGS
Community Advisory Committee meetings for
SR 10 & CR700
PROGRESS
Level 2 Screening Report FINAL,
MEETINGS
Community Office Hours
PROGRESS
Draft Level 3 Screening Report
MEETINGS
PIM (two) and Community Office Hours

## Slide 5
History & Projected Engagement
US 31 Corridor projects
in Marshall & Fulton
2026
2025
PEL FINAL LEVEL 3
Screening Report
(Winter)
US 31 @ SR 10, SR 110, CR 700, 19th ROAD BRIDGE & ACCESS CONTROL
Public Meeting (2/2026)
PEL STUDY COMPLETE
Screening Report
(Summer)
US 31 @ SR 110 & ACCESS CONTROL
CAC3 – Preliminary Preferred Alternative (2/20/2025)
US 31 @ SR 10, SR 110, CR 700, 19th ROAD BRIDGE & ACCESS CONTROL
Public Open House (3/13/2025)
US 31 @ SR 10, SR 110, CR 700, 19th ROAD BRIDGE & ACCESS CONTROL
Public Hearing (9/2026)

## Slide 6
Projected Engagement
US 31 Corridor projects
in Marshall & Fulton
US 31 @ SR 10
US 31 @ CR 700
Construction
Summer 2028
US 31 @ SR 110
US 31 @ Access Control
US 31 @ 19th Road Bridge
Project Letting
December 2029
US 31 @ SR 110
US 31 @ Access Control
US 31 @ 19th Road Bridge
Construction Spring 2030
US 31 @ SR 10 US 31 @ CR 700
Project Letting
February 2028
2028
2030
2029